## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1523 |  |  | Transmital Date: 10/22/2022
Document Title: Process Data Sheets For Close Drain Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1523 |  |  | Transmital Date: 10/22/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | سطوح فرآیندی ظرف، با اعداد مندرج در مدرک Vessel Calculation مغایرت دارد. |  | BK-SUR-ENG-PCS-01-06080 | 2022-11-05 | اصلاح گردید.
2 | نظرات مدرک Vessel Calculation در خصوص این مدرک نیز اعمال گردد. |  | BK-SUR-ENG-PCS-01-06080 | 2022-11-05 | اعمال گردید.
3 | ضروريست نقطه نظرات ذينفع اصلي در خصوص مدرك مذكور اعمال گردد. |  | BK-SUR-ENG-PCS-01-06080 | 2022-11-05 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: | Signature
| Date: 13.08.2022 |  |  |  |  | Date: