## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-PY-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1609 |  |  | Transmital Date: 27-Nov-2022
Document Title: Earthing Layout For Electrical Tower (Gantry) of Well Pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0109-EL-TR-1609 |  |  | Transmital Date: 27-Nov-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بدنه ترانسفورماتور به صورت قطری از دو طرف ارت گردد. در نظر گرفته شود. |  | 1401-2294-392429 | 1401-10-17 | اعمال گردید.
2 | تجهیزات الکتریکی پشت بیرونی شامل کات و اوت فیوز و LBS به همراه جزئیات سیستم ارت مربوطه مطابق استاندارد در مدرک مشخص و نمایش داده شود. |  | 1401-2294-392429 | 1401-10-17 | همانطور که مستحضر هستید، در نقشه Overall SLD مربوط به تسهیلات سرچاهی، تجهیزات الکتریکی شامل کات و اوت فیوز و LBS نمایش داده شده است. لذا خواهشمند است از درج این جزئیات در این مدرک خودداری گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 04-Dec-2022 |  |  |  |  | Date: