## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-PY-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1609 |  |  | Transmital Date: 27-Nov-2022
Document Title: Earthing Layout For Electrical Tower (Gantry) of Well Pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0109-EL-TR-1609 |  |  | Transmital Date: 27-Nov-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-PY-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Earthing layout for gantry of well pads shall be added to this document base on attched existing earthing layout for gantry that has been submitted before. (The earthing layout of tower at the end of transmission line can be shown in "Earthing & Lightning Layout for well pads" document.) |  | BK-SUR-ENG-ELE-01-06339 | 2022-12-04 | مطابق با مذاکرات انجام شده موارد در مدرک لحاظ گردید.
2 | Used attched typical drawing for transmission line tower earthing. |  | BK-SUR-ENG-ELE-01-06339 | 2022-12-04
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 04-Dec-2022 |  |  |  |  | Date: