## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W046S-PEDCO-110-SA-PY-0003-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1784 |  |  | Transmital Date:1/11/2023
Document Title: Escape Route & Safety Sign Layout - W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SA-TR-1784 |  |  | Transmital Date:1/11/2023
[5 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-SA-PY-0003-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است تعداد خاموش کننده های ساختمان برق در قسمت Legend بر اساس نقشه اصلاح شود. |  | 1401-2294-448351 | 1401/11/24 | اعمال گردید
| لازم است یک دستگاه خاموش کننده دستی co2 جهت ساختمان حراست اضافه شود |  | 1401-2294-448351 | 1401/11/24 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021