## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-PI-MR-0008_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1926 |  |  | Transmital Date: 04/03/2023
Document Title: PMR FOR STONE TRAP– W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0112-PI-TR-1926 |  |  | Transmital Date: 04/03/2023
[5 empty] | CRS No: PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0008_D01 |  |  | CRS Status: | C2
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عبارت " List of Documents Will be Finalized in Vendor Document index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-PIP-01-04122 | 2022-02-05 | احتراما در ویرایش D01 مدرک اعمال می گردد. |  |  | See Item No.2
2 | نوت داده شده، در انتهاي جدول پيوست 2، آورده شود. |  | BK-SUR-ENG-PIP-01-07166 | 2023-12-03 | احتراما در ویرایش D02 مدرک اعمال می گردد.
3 | در بند 6: -عبارت "QC Plan" و "Quality Control Plan" به "Inspection and Test Plan (ITP)" تغيير يابد. |  | BK-SUR-ENG-PIP-01-07166 | 2023-12-03 | احتراما در ویرایش D02 مدرک اعمال می گردد.
4 | در جدول پيوست 1، مدرك Packing, Marking, Transportation Procedure اضافه گردد. |  | BK-SUR-ENG-PIP-01-07166 | 2023-12-03 | احتراما در ویرایش D02 مدرک اعمال می گردد.
5 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-PIP-01-07166 | 2023-12-03 | احتراما در ویرایش D02 مدرک اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh M. Torkaman | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature | M.Fakharian
| Date:11/03/2023 |  |  |  |  | Date:11/03/2023