## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0015-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1607 |  |  | Transmital Date: 26-Nov.-2022
Document Title: SPECIFICATION FOR PIPING CONSTRUCTION, FABRICATION & ERECTION |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1607 |  |  | Transmital Date: 26-Nov.-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0015-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 2.3 مدرك زير اضافه شود BK-SSGRL-PEDCO-320-PI-SP-0007 SPECIFICATION FOR LINING INTERNAL PROTECTION OF EQUIPMENT BY PAINTING ) |  | BK-SUR-ENG-PIP-00-01462 | 05-Sep.-2021 | این مشخصات فنی مربوط به پایپینگ می باشد و در پایپینگ Lining نداریم. |  |  | See Item 4
2 | بك بندي تحت عنوان Bending and Forming اضافه شود و توضيحات لازم نوشته شود |  | BK-SUR-ENG-PIP-00-01462 | 05-Sep.-2021 | اعمال گردید. |  |  | See Item 5
3 | با توجه به اينكه LINING در پروژه وجود دارد لذا بند 13 مربوط به LINING به مدرك اضافه شده و توضيحات لازم نوشنه شود |  | BK-SUR-ENG-PIP-00-01462 | 05-Sep.-2021 | این مشخصات فنی مربوط به پایپینگ می باشد و در پایپینگ Lining نداریم. |  |  | See Item 4
4 | با توجه به اينكه در مدرك Piping Corrosion Study & Material Selection Report مربوط به GCS در قسمت 10.3.2 Fuel Gas System براي لوله خروجي مايعات از Fuel Gas K.O. Drum پوشش داخلي در نظر گرفته شده است مدرك زير بايستي اضافه گردد. BK-SSGRL-PEDCO-320-PI-SP-0007 SPECIFICATION FOR LINING INTERNAL PROTECTION OF EQUIPMENT BY PAINTING ) |  | BK-SUR-ENG-PIP-01-06344 | 05-Dec.-2022 | پوشش داخلی صرفا برای خود Fuel gas K.O Drum در نظر گرفته شده است و برای پایپینگ در نظر گرفته نشده است. آخرین ویرایش مدرک مطالعات خوردگی جهت اطلاع پیوست می گردد.
5 | ساير نقطه نظرات روي مدرك درج شده است. |  | BK-SUR-ENG-PIP-01-06344 | 05-Dec.-2022 | در مدرک پاسخ داده شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri M.Torkaman | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date:05-Dec-2022 |  |  |  |  | Date:05-Dec-2022