## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-CN-0004-D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1237 |  |  | Transmital Date: 30-Aug-2022
Document Title: Calculation Note For UPS System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-EL-TR-1237 |  |  | Transmital Date: 30-Aug-2022
[5 empty] | CRS No: NISOC-CRS- BK-GCS-PEDCO-120-EL-CN-0004-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در مدرک به توافق انجام در جلسه اشاره شده،که مورد تایید بخش ابزار دقیق این امور نمی باشد،لذا جهت تعیین سایز UPS لازم است که محاسبات اصلاحی پس از تایید لیست بار سیستم های کنترل توسط بخش ابزار دقیق این امور اقدامات مقتضی بعمل آید. |  | 1401-2294-205602 | 1401-06-09 | این مدرک بر اساس آخرین ویرایش I&C Power Consumption Summary که با ترنسمیتال 1692 تولید شده، ویرایش گردیده و در صورت تغییر لیست بار ابزاردقیق تغییر خواهد کرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Gh.Saadatian | Signature |  |  |  | Clarified By: | Signature
| Date: 17-Aug-22 |  |  |  |  | Date: