## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0019_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1663 |  |  | Transmital Date: 6 Dec 2022
Document Title: Data Sheets For Diff. Pressure Type Level Transmitter |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-T-1663 |  |  | Transmital Date: 6 Dec 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0019_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ضروریست در کلیه مدارک ویرایش درج شده جهت مدرک P&ID اصلاح گردد |  | 01/2294/385230 | 1401/10/11 | مطابق درخواست کارفرمای محترم اعمال گردید
2 | سیگنال خروجی بصورت Smart Hart mA 4˷20 اصلاح گردد |  | 01/2294/385230 | 1401/10/11 | کارفرمای محترم در بند 36 مدارک به این نکته اشاره شده است
3
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: