## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-CN-0005-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1018 |  |  | Transmital Date: 29-May-2022
Document Title: Calculation Note For DC Charger System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-EL-TR-1018 |  |  | Transmital Date: 29-May-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-CN-0005-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | روش سایزینگ بررسی گردیده و نظر خاصی مطرح نمی باشد. |  | 1401-2294-122076 | 1401-04-04 | با سپاس
2 | لازم است جهت جلوگیری از Over Size شدن بی مورد دستگاهها، مدرک سایزینگ باتری وباتری شارژرهای 24 و110 ولت، پس از نهایی سازی جداول بار، با جداول بار واقعی نهایی و تایید شده، مورد بازنگری مجدد قرار گیرد و در صورت نیاز به روزرسانی و اصلاح گردند. |  | 1401-2294-122076 | 1401-04-04 | همانطور که مستحضر هستید مدرک محاسباتی UPS در کامنت شیت شماره 205602 بر روی ترنسمیتال 1237، AN شده است. همچنین این مدرک از لحاظ نحوه محاسبات مورد تایید کارشناسان محترم شرکت پترو ایران می باشد لذا از آنجا که براساس ترنسمیتال 1692 آخرین محاسبات بخش ابزاردقیق با اعداد این مدرک همخوانی دارد این مدرک به صورت نهایی ارسال می گردد. در صورت هر گونه تغییر در مدرک ابزار دقیق این مدرک ویرایش خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 11-Jun-22 |  |  |  |  | Date: