## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-NISOC-T-1299 |  |  | Transmital Date: 22 Aug 2022
Document Title: PMR For Control Valves |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1299 |  |  | Transmital Date: 22 Aug 2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جدول صفحه 5 مربوط به قسمت Subject of the supply ، با توجه به نقشه های P&ID نهایی بروز رسانی گردد. |  | 01/2294/216179 | 1401/06/17 | مدرک مطابق آخرین نسخه از مدرک P&ID اصلاح و بروز رسانی گردید.
2 | صفحه 10 قسمت 11، عبارت Other fee(if any) حذف گردد. |  | 01/2294/216179 | 1401/06/17 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
2 | عبارت (if required) و (if any) از مدرک حذف گردد. |  | 01/2294/216179 | 1401/06/17 | مدرک مطابق خواست کارفرمای محترم اصلاح گردید.
3 | آخرین ویرایش مدارک پیوست مد نظر قرار گیرد. |  | 01/2294/216179 | 1401/06/17 | آخرین نسخه از مدارک پیوست در جدول ATTACHMENT 1 مد نظر قرارگرفته است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 3 sep 2022 |  |  |  |  | Date: