## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 3
9184 – 073 - 053 |  |  | BK |  | GCS | AA | 120 |  | PM | LI | 0001 | V00
طرح نگهداشت و افزایش تولید 27 مخزن
VENDOR PRINT INDEX & SCHEDULE (VPIS) نگهداشت و افزایش تولید میدان نفتی بینک
V00 |  | NOV.2023 |  | IFA |  |  |  | AAC |  |  | M.Fakharian |  | S.Faramarzpour
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
CLIENT Doc. Number:
status:
IFI: Issued For Information
IFA: Issued For Approval
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 3
9184 – 073 - 053 |  |  | BK | GCS |  | AA | 120 | PM | LI | 0001 |  | V00
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | [7 empty] | 65
2 | X | [7 empty] | 66
3 | X | [7 empty] | 67
4 | [8 empty] | 68
5 | [8 empty] | 69
6 | [8 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## VPIS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | نسخه | شماره صفحه: 3 از 3
9184 – 073 - 053 |  | BK | GCS | AA | 120 | PM | LI | 0001 | V00
S/R No. | Doc. No. | Document Description | [7 empty] | Status | Remarks
1 | General/ Management
1.1 | List
1.1.1 | BK-GCS-AA-120-PM-LI-0001 | Vendor Print Index & Schedule (VPIS) | [7 empty] | IFA
1.1.2 | BK-GCS-AA-120-PM-WB-0001 | Work Breakdown Structure | [7 empty] | IFA
1.1.3 | BK-GCS-AA-120-GE-VL-0001 | Sub-vendor List | [7 empty] | IFA
1.1.4 | BK-GCS-AA-120-GE-SH-0001 | Time Schedule | [7 empty] | IFA
1.1.5 | BK-GCS-AA-120-GE-LI-0002 | Spare Part List | [7 empty] | IFA
1.1.6 | BK-GCS-AA-120-GE-LI-0003 | Final Data Book Index | [7 empty] | IFA
1.2 | Drawing/Diagram
1.2.1 | BK-GCS-AA-120-GE-DW-0001 | Name Plate Drawing | [7 empty] | IFA
1.3 | Reports
1.3.1 | BK-GCS-AA-120-GE-DO-0001 | Final Data Book | [7 empty] | IFA
2 | QA/QC
2.1 | Procedure/Plan
2.1.1 | BK-GCS-AA-120-QC-PR-0001 | Inspection & Test Plan (ITP) | [7 empty] | IFA
2.1.2 | BK-GCS-AA-120-QC-PR-0002 | Quality Control Plan (QCP) | [7 empty] | IFI
2.1.3 | BK-GCS-AA-120-QC-PR-0003 | W.P.S & P.Q.R | [7 empty] | IFA
2.1.4 | BK-GCS-AA-120-QC-PR-0004 | Surface Preparation and Painting Procedure (w/ Paint Datasheet) | [7 empty] | IFA
2.1.5 | BK-GCS-AA-120-QC-PR-0005 | NDE Procedure | [7 empty] | IFA
2.1.6 | BK-GCS-AA-120-QC-PR-0006 | Hydrostatic Test Procedure | [7 empty] | IFA
2.1.7 | BK-GCS-AA-120-QC-PR-0007 | SAT (Performance Test) Procedure | [7 empty] | IFA
2.2 | Manual
2.2.1 | BK-GCS-AA-120-QC-ML-0001 | Installation, Operation & Maintenance Manual | [7 empty] | IFI
3 | Process
3.1 | Calculation
3.1.1 | BK-GCS-AA-120-PR-CN-0001 | Thermal/Mechanical Calculation Books | [7 empty] | IFA
3.2 | Datasheet
3.2.1 | BK-GCS-AA-120-PR-DS-0001 | Process Data Sheet for AE-2101 (A/B/C) | [7 empty] | IFA
3.2.2 | BK-GCS-AA-120-PR-DS-0002 | Process Data Sheet for AE-2102 (A/B/C) | [7 empty] | IFA
3.3 | Diagram
3.3.1 | BK-GCS-AA-120-PR-PI-0001 | P&ID | [7 empty] | IFA
3.4 | List
3.4.1 | BK-GCS-AA-120-PR-LI-0001 | Utility Consumption List | [7 empty] | IFI
4 | Mechanical
4.1 | Drawing
4.1.1 | BK-GCS-AA-120-ME-DW-0001 | General Arrangement Drawings | Tube Bundle Detail Drawing for 44E-60001 for Air Coolers (2) | Tube Bundle Detail Drawing for 44E-60001 for Air Coolers (2) | Tube Bundle Detail Drawing for 44E-60001 for Air Coolers (2) | Tube Bundle Detail Drawing for 44E-60001 for Air Coolers (2) | Tube Bundle Detail Drawing for 44E-60001 for Air Coolers (2) | Tube Bundle Detail Drawing for 44E-60001 for Air Coolers (2) | Tube Bundle Detail Drawing for 44E-60001 for Air Coolers (2) | IFI
4.2 | Datasheet
4.2.1 | BK-GCS-AA-120-ME-DS-0001 | Fan Data Sheets | Fan Data Sheet for 44E-60001 for Air Coolers (2) | Fan Data Sheet for 44E-60001 for Air Coolers (2) | Fan Data Sheet for 44E-60001 for Air Coolers (2) | Fan Data Sheet for 44E-60001 for Air Coolers (2) | Fan Data Sheet for 44E-60001 for Air Coolers (2) | Fan Data Sheet for 44E-60001 for Air Coolers (2) | Fan Data Sheet for 44E-60001 for Air Coolers (2) | IFA
4.2.2 | BK-GCS-AA-120-ME-DS-0002 | Pulley Data Sheets | Pulley Data Sheet for 44E-60001 for Air Coolers (2) | Pulley Data Sheet for 44E-60001 for Air Coolers (2) | Pulley Data Sheet for 44E-60001 for Air Coolers (2) | Pulley Data Sheet for 44E-60001 for Air Coolers (2) | Pulley Data Sheet for 44E-60001 for Air Coolers (2) | Pulley Data Sheet for 44E-60001 for Air Coolers (2) | Pulley Data Sheet for 44E-60001 for Air Coolers (2) | IFA
5 | Instrument
5.1 | Datasheet
5.1.1 | BK-GCS-AA-120-IN-DS-0001 | Pulley Data Sheets | [7 empty] | IFA
5.1.2 | BK-GCS-AA-120-IN-DS-0002 | Vibration Switch Data Sheets and Catalogue | Vibration Switch Data Sheet and Catalogue for 44E-60001 for Air Coolers (2) | Vibration Switch Data Sheet and Catalogue for 44E-60001 for Air Coolers (2) | Vibration Switch Data Sheet and Catalogue for 44E-60001 for Air Coolers (2) | Vibration Switch Data Sheet and Catalogue for 44E-60001 for Air Coolers (2) | Vibration Switch Data Sheet and Catalogue for 44E-60001 for Air Coolers (2) | Vibration Switch Data Sheet and Catalogue for 44E-60001 for Air Coolers (2) | Vibration Switch Data Sheet and Catalogue for 44E-60001 for Air Coolers (2) | IFA
6 | Electrical
6.1 | Datasheet
6.1.1 | BK-GCS-AA-120-EL-DS-0001 | Motor Data Sheets | [7 empty] | IFA
6.2 | List
6.2.1 | BK-GCS-AA-120-EL-LI-0001 | Electrical Load List | [7 empty] | IFI
7 | Structure
7.1 | Calculation
7.1.1 | BK-GCS-AA-120-ST-CN-0001 | Steel Structure Calculation Books | [7 empty] | IFA
7.2 | Drawing
7.2.1 | BK-GCS-AA-120-ST-PI-0001 | Steel Structure Drawings | Steel Structure Drawing for 44E-60001 for Air Coolers (2) | Steel Structure Drawing for 44E-60001 for Air Coolers (2) | Steel Structure Drawing for 44E-60001 for Air Coolers (2) | Steel Structure Drawing for 44E-60001 for Air Coolers (2) | Steel Structure Drawing for 44E-60001 for Air Coolers (2) | Steel Structure Drawing for 44E-60001 for Air Coolers (2) | Steel Structure Drawing for 44E-60001 for Air Coolers (2) | IFA
7.2.2 | BK-GCS-AA-120-ST-PI-0002 | Foundation Drawings | [7 empty] | IFA