## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-PR-CN-0001-V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: Thermal/Mechanical Calculation Books |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0003 |  |  | Transmital Date: 2024/03/09
[5 empty] | CRS No:NISOC-CRS-BK-GCS-AA-120-PR-CN-0001_V00 |  |  | CRS Status: | CM
| Comments (NISOC) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
متریال (مطابق با مدارک پروژه) S.S.-316L میباشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC) |  |  |  |  | EPC Contractor
| Commented By: Al.Ahmadi P.Maleki | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 13/Dec/2023 |  |  |  |  | Date: