## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-PR-DS-0001-V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: Process Data Sheet for AE-2101 (A/B/C) |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0003 |  |  | Transmital Date: 2024/03/09
[5 empty] | CRS No:NISOC-CRS-BK-GCS-AA-120-PR-DS-0001_V00 |  |  | CRS Status: | CM
| Comments (PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Process comments :
|  |  | 02-2294-438763 | 1402/10/26 | با توجه به آخرین P&ID پکیج کمپرسورهای گاز (هوایار)، فشار طراحی کولرهای مرحله اول 22Barg می باشد.
سایزینگ الکتروموتور در کولرهای هوایی طبق الزامات استاندارد API-661 صورت می پذیرد (که درحال حاضر نیز این شرایط کاملا رعایت شده است).
در خصوص IP موتور، درحال حاضر IP55 (بدون W) قابل تامین میباشد.
سایر موارد مورد تایید است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 13/Dec/2023 |  |  |  |  | Date: