## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-ME-DW-0001-V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: GENERAL ARRANGEMENT DRAWINGS |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0006 |  |  | Transmital Date: 2024/04/07
[5 empty] | CRS No: NISOC-CRS-BK-GCS-AA-120-ME-DW-0001-V00 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Process comments :
|  |  | 02/2294/530395 | 1402/12/20 | 1- در حوزه تامین ابان نبوده و یک پلتفرم قابل حمل … جهت آن دیده شده است .
2- تامین روشنایی در حوزه ابان نمی باشد .
3-1 : دیتاشیت موتور ارایه می گردد . 3-2 : در حوزه ابان نمی باشد . 3-3 : مورد تایید می باشد .
4-تامین در حوزه ابان نمی باشد ، لذا این مورد بایستی در GA توسط کارفرمای محترم و بر اساس مسیر کابل تعیین گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 13/Dec/2023 |  |  |  |  | Date: