## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-PM-LI-0001-V00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-SVTR-AA-0001 |  |  | Transmital Date: 11/Nov/2023
Document Title: VENDOR PRINT INDEX & SCHEDULE (VPIS) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0208-PM-TR-AA-0001 |  |  | Transmital Date: 13/Nov/2023
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-AA-120-PM-LI-0001 |  |  | CRS Status: | C2
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Mechanical Comments :
1 | در خصوص Mechanical equipment list و دیتا شیت های مكانيكال متناظر آن شفاف سازي گردد.اطلاعات مكانيكال در چه مدركي آورده مي شود؟ |  | BK-SUR-ENG-MEC-02-08810 | 21/Nov/2023
2 | نسبت به ارسال مدارک مطابق با عناوین قید شده در MR تجهیز اقدام گردد |  | BK-SUR-ENG-MEC-02-08810 | 21/Nov/2023
| Performance curves به مدرك اضافه گردد. |  | BK-SUR-ENG-MEC-02-08810
QC comments :
1 | مدارك ذيل به ليست اضافه گردد: Welding and NDT Map Pickling & Passivation Procedure Ferrite Number Measurment Procedure Drying Procedure N2 Purging Procedure Electro Motor Routine Test Procedure Packing,Marking,Shipping Procedure ( PMI Procedure ( welding of stainless steel |  | BK-SUR-ENG-MEC-02-08810 | 2023-11-21 | .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Al.Ahmadi Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 21/Nov/2023 |  |  |  |  | Date: