## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-PM-LI-0001-V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: Vendor Print Index & Schedule (VPIS) |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0001 |  |  | Transmital Date: 2024/04/22
[5 empty] | CRS No: NISOC-CRS- BK-GCS-AA-120-PM-LI-0001_V00 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Process comments :
|  |  | 02/2294/530221 | 1402/12/20 | 1- با توجه به اینکه کولر های هوایی UCP مجزا ندارند ، Logic آن در مدارک ایستگاه دیده شده است.
NOTED-2
3-دیتاشت های فن ،بلت، و پولی قبلا در VPIS اشاره شده است.
4-در قالب BLOCK/ PART LIST ارایه می گردد
5-مدرک SATقبلا اضافه گردیده است.
6-7-8: همگی در مدرک موتور دیتا شیت آورده می شوند
9-NOTED
10-در فاینال بوک آورده می شود
11-در MOTOR DATA SHEET آورده می شود
12-در قالب مدرک ELECTRIC MOTOR ROUTARI PROCEDURE آورده می شود
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 13/Dec/2023 |  |  |  |  | Date: