## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
WORK BREAKDOWN STRUCTURE
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 4
9184 – 073 - 053 |  |  | BK |  | GCS | AA | 120 |  | PM | WB | 0001 | V00
طرح نگهداشت و افزایش تولید 27 مخزن
WORK BREAKDOWN STRUCTURE نگهداشت و افزایش تولید میدان نفتی بینک
V00 |  | May. 2024 |  | IFA |  |  |  | AAC |  |  | M.Fakharian |  | S.Faramarzpour
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
CLIENT Doc. Number:
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
Work Breakdown Structure
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 4
9184 – 073 - 053 |  |  | BK | GCS |  | AA | 120 | PM | WB | 0001 |  | V00
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | [7 empty] | 65
2 | X | [7 empty] | 66
3 | X | [7 empty] | 67
4 | X | [7 empty] | 68
5 | [8 empty] | 69
6 | [8 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## WBS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
Work Breakdown Structure
شماره پیمان: | BK-GCS-AA-120-PM-WB-0001_V00 | شماره صفحه: 3 از 4
9184 – 073 - 053
|  | Total Weight Factor | Weight Factor Sub-Level
WBS |  |  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5
1 | project Air Cooler(Binak Oilfield Development , New Gas Commpressor Station) | 100 | 100
1.1 | Before Manufacturing | 10 |  | 10
1.1.1 | Pre-Inspection Meeting (PIM) | 1 |  |  | 10
1.1.2 | Documentation | 8.8 |  |  | 88
1.1.2.1 | Vendor Print Index & Schedule (VPIS) | 0.88 |  |  |  | 10
1.1.2.2 | Work Breakdown Structure | 0.88 |  |  |  | 10
1.1.2.3 | Sub-vendor List | 0.44 |  |  |  | 5
1.1.2.4 | Time Schedule | 0.616 |  |  |  | 7
1.1.2.5 | Spare Part List | 0.088 |  |  |  | 1
1.1.2.6 | Final Data Book Index | 0.088 |  |  |  | 1
1.1.2.7 | Name Plate Drawing | 0.088 |  |  |  | 1
1.1.2.8 | Final Data Book | 0.088 |  |  |  | 1
1.1.2.9 | Inspection & Test Plan (ITP) | 0.88 |  |  |  | 10
1.1.2.10 | Quality Control Plan (QCP) | 0.088 |  |  |  | 1
1.1.2.11 | W.P.S & P.Q.R | 0.088 |  |  |  | 1
1.1.2.12 | Surface Preparation and Painting Procedure (w/ Paint Datasheet) | 0.088 |  |  |  | 1
1.1.2.13 | NDE Procedure | 0.088 |  |  |  | 1
1.1.2.14 | Hydrostatic Test Procedure | 0.088 |  |  |  | 1
1.1.2.15 | SAT (Performance Test) Procedure | 0.44 |  |  |  | 5
1.1.2.16 | Installation, Operation & Maintenance Manual | 0.44 |  |  |  | 5
1.1.2.17 | Thermal/Mechanical Calculation Books | 0.44 |  |  |  | 5
1.1.2.18 | Process Data Sheet for AE-2101 (A/B/C) | 0.088 |  |  |  | 1
1.1.2.19 | Process Data Sheet for AE-2102 (A/B/C) | 0.088 |  |  |  | 1
1.1.2.20 | P&ID | 0.44 |  |  |  | 5
1.1.2.21 | Utility Consumption List | 0.44 |  |  |  | 5
1.1.2.22 | General Arrangement Drawings | 0.88 |  |  |  | 10
1.1.2.23 | Fan Data Sheets | 0.088 |  |  |  | 1
1.1.2.24 | Pulley Data Sheets | 0.088 |  |  |  | 1
1.1.2.25 | Vibration Switch Data Sheets and Catalogue | 0.088 |  |  |  | 1
1.1.2.26 | Motor Data Sheets | 0.088 |  |  |  | 1
1.1.2.27 | Electrical Load List | 0.176 |  |  |  | 2
1.1.2.28 | Steel Structure Calculation Books | 0.176 |  |  |  | 2
1.1.2.29 | Steel Structure Drawings | 0.176 |  |  |  | 2
1.1.2.30 | Foundation Drawings | 0.176 |  |  |  | 2
1.1.3 | Measuring & Test Equipment Calibration | 0.1 |  |  | 1
1.1.4 | NDT Personal Qualification for Air Coolers | 0.1 |  |  | 1
1.2 | Material Inspection | 40 |  | 40
1.2.1 | Verification of Raw Material (Including plate , tube , pipe) | 20 |  |  | 50
1.2.2 | Verification of Raw Material (Including flange, gasket , plug , bolt/ nut , ...) | 18 |  |  | 45
1.2.3 | Verification of Consumables Material (Including Welding Consumables, Abbrasive , paint.) | 1.6 |  |  | 4
1.2.4 | Storage of materials & welding consumable | 0.4 |  |  | 1
1.3 | During Manufacturing | 25 |  | 25
1.3.1 | Material Identification and Traceability and TRANSFER OF MATERIAL IDENTIFICATION BEFORE CUTTING | 5 |  |  | 20
1.3.2 | Visual & dimensional Inspection of joint Preparation (Beveling Inspection). | 1.25 |  |  | 5
1.3.3 | PT Examination for , beveling, | 1.25 |  |  | 5
1.3.4 | Fit-up and welding | 1.25 |  |  | 5
1.3.5 | PT root pass and back gouging | 1.25 |  |  | 5
1.3.6 | Ferrite number measurement | 1.25 |  |  | 5
1.3.7 | PT of Welds | 0.25 |  |  | 1
1.3.8 | Ultrasonic Examination | 0.25 |  |  | 1
1.3.9 | Radiographic Examination & film interpretation | 0.25 |  |  | 1
1.3.10 | Welding Major Repair | 0.25 |  |  | 1
1.3.11 | Visual and Dimensional Inspection of Header Boxes & alignment check (Nozzle to flange and header) | 1 |  |  | 4
1.3.12 | PMI of welding stainless steel | 1.25 |  |  | 5
1.3.13 | Drilling & machining | 1.25 |  |  | 5
1.3.14 | Visual & Dimensional Inspection after drilling & machining | 0.25 |  |  | 1
1.3.15 | Pickling and passivation | 1.25 |  |  | 5
1.3.16 | Visual & Dimensional assembly side frame | 1.25 |  |  | 5
1.3.17 | Tube to tube sheet welding | 1.25 |  |  | 5
1.3.18 | Finned Tube Inspection Visual and dimensional check | 3.75 |  |  | 15
1.3.19 | Tube expanding | 1.25 |  |  | 5
1.3.20 | PT for tube to tube sheet joint | 0.25 |  |  | 1
1.4 | Final Inspection | 10 |  | 10
1.4.1 | Inspection for Completed Tube Bundle | 5 |  |  | 50
1.4.1.1 | Visual & Dimensional Inspection | 2.5 |  |  |  | 50
1.4.1.2 | Hydro Test | 2.25 |  |  |  | 45
1.4.1.3 | Drying , N2 purging | 0.25 |  |  |  | 5
1.4.2 | Fan and driver assembly inspection | 0.5 |  |  | 5
1.4.2.1 | Visual & Dimensional Inspection | 0.25 |  |  |  | 50
1.4.2.2 | Balance test for pulley& belt | 0.1 |  |  |  | 20
1.4.2.3 | Assembly of rotating parts inspection | 0.05 |  |  |  | 10
1.4.2.4 | Balance test for fan blades and hubs and Shaft | 0.05 |  |  |  | 10
1.4.2.5 | Louver visual and dimentional & coating check | 0.05 |  |  |  | 10
1.4.3 | Electric Motor Inspection | 0.5 |  |  | 5
1.4.3.1 | Type test | 0.2 |  |  |  | 40
1.4.3.2 | Routine test | 0.2 |  |  |  | 40
1.4.3.3 | IP & ExX certificate rewiew | 0.1 |  |  |  | 20
1.4.4 | Instruments | 0.5 |  |  | 5
1.4.4.1 | I/P Convertor | 0.25 |  |  |  | 50
1.4.4.1.1 | Visual inspection | 0.2 |  |  |  |  | 80
1.4.4.1.2 | Calibration | 0.025 |  |  |  |  | 10
1.4.4.1.3 | IP & ExX certificate rewiew | 0.025 |  |  |  |  | 10
1.4.4.2 | Vibration Switch | 0.25 |  |  |  | 50
1.4.4.2.1 | Visual inspection | 0.2 |  |  |  |  | 80
1.4.4.2.2 | Test certificate | 0.025 |  |  |  |  | 10
1.4.4.2.3 | IP & ExX certificate rewiew | 0.025 |  |  |  |  | 10
1.4.5 | Steel Structure Inspection | 3.5 |  |  | 35
1.4.5.1 | Material certificate check | 1.75 |  |  |  | 50
1.4.5.2 | Steel member visual & Dimensional Inspection | 0.7 |  |  |  | 20
1.4.5.3 | Welding of steel structure | 0.7 |  |  |  | 20
1.4.5.4 | NDT after welding if any | 0.175 |  |  |  | 5
1.4.5.5 | Surface Preparation and Painting Inspection (including Side frame, fan ring, plenum, …) | 0.175 |  |  |  | 5
1.5 | Spare part Inspection | 5 |  | 5
1.5.1 | Material certificate review | 2.5 |  |  | 50
1.5.2 | VT, DT, Quantities and packing | 2.5 |  |  | 50
1.6 | Pre shippment Inspection | 10 |  | 10
1.6.1 | Prepration for shippment ( shipping mark Check) | 4 |  |  | 40
1.6.2 | Packing and Marking check (Including Packing Condition and Quantity and spare part check) | 1 |  |  | 10
1.6.3 | Touch up and Name plate stamping ( befor attaching) | 1 |  |  | 10
1.6.4 | manufacturer certificate of compliance | 0.5 |  |  | 5
1.6.5 | Issue Inspection Release Note (IRN) / Shipping Release Note by TPA | 1.5 |  |  | 15
1.6.6 | Final data book | 1 |  |  | 10
1.6.7 | IC | 0.5 |  |  | 5
1.6.8 | SAT | 0.5 |  |  | 5