## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
WORK BREAKDOWN STRUCTURE
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 4
9184 – 073 - 053 |  |  | BK |  | GCS | AA | 120 |  | PM | WB | 0001 | V01
طرح نگهداشت و افزایش تولید 27 مخزن
WORK BREAKDOWN STRUCTURE نگهداشت و افزایش تولید میدان نفتی بینک
V01 |  | Jul. 2024 |  | IFA |  |  |  | AAC |  |  | M.Fakharian |  | M.Sadeghian
V00 |  | May. 2024 |  | IFA |  |  |  | AAC |  |  | M.Fakharian |  | S.Faramarzpour
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
CLIENT Doc. Number:
status:
IFA: Issued For Approval
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
Work Breakdown Structure
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 4
9184 – 073 - 053 |  |  | BK | GCS |  | AA | 120 | PM | WB | 0001 |  | V01
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | X | [6 empty] | 65
2 | X | X | [6 empty] | 66
3 | X | X | [6 empty] | 67
4 | X | X | [6 empty] | 68
5 | [8 empty] | 69
6 | [8 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## WBS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج کولرهای هوایی ایستگاه تقویت فشار گاز بینک (قرارداد BK-HD-GCS-CO-0015_02)
Work Breakdown Structure
شماره پیمان: | BK-GCS-AA-120-PM-WB-0001_V01 | شماره صفحه: 3 از 4
9184 – 073 - 053
|  | Total Weight Factor | Weight Factor Sub-Level
WBS |  |  | Level 1 | Level 2 | Level 3 | Level 4 | Level 5
1 | project Air Cooler(Binak Oilfield Development , New Gas Commpressor Station) | 100
1.1 | Before Manufacturing | 5 | 5
1.1.1 | Pre-Inspection Meeting (PIM) | 0.5 |  | 10
1.1.2 | Documentation | 4.5 |  | 90
1.1.2.1 | General/ Management | 0.45 |  |  | 10
1.1.2.1.1 | list | 0.36 |  |  |  | 80
1.1.2.1.1.1 | Vendor Print Index & Schedule (VPIS) | 0.072 |  |  |  |  | 20
1.1.2.1.1.2 | Work Breakdown Structure | 0.072 |  |  |  |  | 20
1.1.2.1.1.3 | Sub-vendor List | 0.072 |  |  |  |  | 20
1.1.2.1.1.4 | Time Schedule | 0.072 |  |  |  |  | 20
1.1.2.1.1.5 | Spare Part List | 0.036 |  |  |  |  | 10
1.1.2.1.1.6 | Final Data Book Index | 0.036 |  |  |  |  | 10
1.1.2.1.2 | Drawing/Diagram | 0.045 |  |  |  | 10
1.1.2.1.2.1 | Name Plate Drawing | 0.045 |  |  |  |  | 100
1.1.2.1.3 | Reports | 0.045 |  |  |  | 10
1.1.2.1.3.1 | Final Data Book | 0.045 |  |  |  |  | 100
1.1.2.2 | QA/QC | 0.45 |  |  | 10
1.1.2.2.1 | Procedure/Plan | 0.36 |  |  |  | 80
1.1.2.2.1.1 | Inspection & Test Plan (ITP) | 0.108 |  |  |  |  | 30
1.1.2.2.1.2 | Quality Control Plan (QCP) | 0.036 |  |  |  |  | 10
1.1.2.2.1.3 | W.P.S & P.Q.R | 0.036 |  |  |  |  | 10
1.1.2.2.1.4 | Surface Preparation and Painting Procedure (w/ Paint Datasheet) | 0.036 |  |  |  |  | 10
1.1.2.2.1.5 | NDE Procedure | 0.018 |  |  |  |  | 5
1.1.2.2.1.6 | Hydrostatic Test Procedure | 0.018 |  |  |  |  | 5
1.1.2.2.1.7 | SAT (Performance Test) Procedure | 0.018 |  |  |  |  | 5
1.1.2.2.1.8 | Pickling & Passivation Procedure | 0.018 |  |  |  |  | 5
1.1.2.2.1.9 | Ferrite Number Measurment Procedure | 0.018 |  |  |  |  | 5
1.1.2.2.1.10 | N2 Purging Procedure | 0.018 |  |  |  |  | 5
1.1.2.2.1.11 | PMI Procedure ( welding of stainless steel) | 0.018 |  |  |  |  | 5
1.1.2.2.1.12 | Packing,Marking,Shipping Procedure | 0.018 |  |  |  |  | 5
1.1.2.2.2 | Drawing | 0.045 |  |  |  | 10
1.1.2.2.2.1 | Welding and NDT Map | 0.045 |  |  |  |  | 100
1.1.2.2.3 | List | 0.045 |  |  |  | 10
1.1.2.2.3.1 | Packing List | 0.045 |  |  |  |  | 100
1.1.2.3 | Process | 0.9 |  |  | 20
1.1.2.3.1 | Calculation | 0.36 |  |  |  | 40
1.1.2.3.1.1 | Thermal / Mechanical Calculation Book | 0.36 |  |  |  |  | 100
1.1.2.3.2 | Datasheet | 0.36 |  |  |  | 40
1.1.2.3.2.1 | Process Data Sheet for AE-2101 (A/B/C) | 0.18 |  |  |  |  | 50
1.1.2.3.2.2 | Process Data Sheet for AE-2102 (A/B/C) | 0.18 |  |  |  |  | 50
1.1.2.3.3 | Diagram | 0.09 |  |  |  | 10
1.1.2.3.3.1 | P&ID | 0.09 |  |  |  |  | 100
1.1.2.3.4 | List | 0.09 |  |  |  | 10
1.1.2.3.4.1 | Utility Consumption List | 0.09 |  |  |  |  | 100
1.1.2.4 | Mechanical | 1.8 |  |  | 40
1.1.2.4.1 | Drawing | 0.72 |  |  |  | 40
1.1.2.4.1.1 | General Arrangement Drawings | 0.18 |  |  |  |  | 25
1.1.2.4.1.2 | Tube Bundle Drawing | 0.108 |  |  |  |  | 15
1.1.2.4.1.3 | Side Frame Drawing | 0.072 |  |  |  |  | 10
1.1.2.4.1.4 | Fan & Pulley Gaurd Drawing | 0.036 |  |  |  |  | 5
1.1.2.4.1.5 | Driving Assembly Drawing | 0.036 |  |  |  |  | 5
1.1.2.4.1.6 | Plenum fan Ring Drawing | 0.072 |  |  |  |  | 10
1.1.2.4.1.7 | Upper, Lower Bearing Drawing | 0.036 |  |  |  |  | 5
1.1.2.4.1.8 | Shaft Housing Drawing | 0.036 |  |  |  |  | 5
1.1.2.4.1.9 | Drive shaft Drawing | 0.036 |  |  |  |  | 5
1.1.2.4.1.10 | Fan & Motor Support Drawing | 0.036 |  |  |  |  | 5
1.1.2.4.1.11 | Name Plate Drawing | 0.036 |  |  |  |  | 5
1.1.2.4.1.12 | Louver Drawing | 0.036 |  |  |  |  | 5
1.1.2.4.2 | Datasheet | 0.72 |  |  |  | 40
1.1.2.4.2.1 | Fan Data Sheets | 0.432 |  |  |  |  | 60
1.1.2.4.2.2 | Pulley Data Sheets | 0.144 |  |  |  |  | 20
1.1.2.4.2.3 | Pneumatic Actuator Data Sheet for Blades | 0.144 |  |  |  |  | 20
1.1.2.4.3 | LIST | 0.18 |  |  |  | 10
1.1.2.4.3.1 | Special tools List | 0.054 |  |  |  |  | 30
1.1.2.4.3.2 | Block/ Part List | 0.036 |  |  |  |  | 20
1.1.2.4.3.3 | Spare Part List for two years operation | 0.09 |  |  |  |  | 50
1.1.2.4.4 | Manual | 0.18 |  |  |  | 10
1.1.2.4.4.1 | Installation, Operation & Maintenance Manual | 0.18 |  |  |  |  | 100
1.1.2.5 | Instrument | 0.225 |  |  | 5
1.1.2.5.1 | Datasheet | 0.225 |  |  |  | 100
1.1.2.5.1.1 | Pulley Data Sheets | 0.045 |  |  |  |  | 20
1.1.2.5.1.2 | Vibration Switch Data Sheets and Catalogue | 0.09 |  |  |  |  | 40
1.1.2.5.1.3 | IP Converter Data Sheet | 0.09 |  |  |  |  | 40
1.1.2.6 | Electrical | 0.225 |  |  | 5
1.1.2.6.1 | Datasheet | 0.1125 |  |  |  | 50
1.1.2.6.1.1 | Motor Data Sheets Including Curves and Drawing | 0.1125 |  |  |  |  | 100
1.1.2.6.2 | List | 0.09 |  |  |  | 40
1.1.2.6.2.1 | Electrical Load List | 0.09 |  |  |  |  | 100
1.1.2.6.3 | Procedure | 0.0225 |  |  |  | 10
1.1.2.6.3.1 | Electro Motor Routine Test Procedure | 0.0225 |  |  |  |  | 100
1.1.2.7 | Structure | 0.45 |  |  | 10
1.1.2.7.1 | Calculation | 0.225 |  |  |  | 50
1.1.2.7.1.1 | Steel Structure Calculation Books | 0.225 |  |  |  |  | 100
1.1.2.7.2 | Drawing | 0.225 |  |  |  | 50
1.1.2.7.2.1 | Steel Structure Drawings | 0.18 |  |  |  |  | 80
1.1.2.7.2.2 | Foundation Drawings | 0.045 |  |  |  |  | 20
1.2 | Material Inspection | 30 | 30
1.2.1 | Verification of Raw Material (Including plate , tube , pipe) | 15 |  | 50
1.2.2 | Verification of Raw Material (Including flange, gasket , plug , bolt/ nut , ...) | 13.5 |  | 45
1.2.3 | Verification of Consumables Material (Including Welding Consumables, Abbrasive , paint.) | 1.2 |  | 4
1.2.4 | Storage of materials & welding consumable | 0.3 |  | 1
1.3 | During Manufacturing | 40 | 40
1.3.1 | Material Identification and Traceability and TRANSFER OF MATERIAL IDENTIFICATION BEFORE CUTTING | 8 |  | 20
1.3.2 | Visual & dimensional Inspection of joint Preparation (Beveling Inspection). | 2 |  | 5
1.3.3 | PT Examination for , beveling, | 2 |  | 5
1.3.4 | Fit-up and welding | 2 |  | 5
1.3.5 | PT root pass and back gouging | 2 |  | 5
1.3.6 | Ferrite number measurement | 2 |  | 5
1.3.7 | PT of Welds | 0.4 |  | 1
1.3.8 | Ultrasonic Examination | 0.4 |  | 1
1.3.9 | Radiographic Examination & film interpretation | 0.4 |  | 1
1.3.10 | Welding Major Repair | 0.4 |  | 1
1.3.11 | Visual and Dimensional Inspection of Header Boxes & alignment check (Nozzle to flange and header) | 1.6 |  | 4
1.3.12 | PMI of welding stainless steel | 2 |  | 5
1.3.13 | Drilling & machining | 2 |  | 5
1.3.14 | Visual & Dimensional Inspection after drilling & machining | 0.4 |  | 1
1.3.15 | Pickling and passivation | 2 |  | 5
1.3.16 | Visual & Dimensional assembly side frame | 2 |  | 5
1.3.17 | Tube to tube sheet welding | 2 |  | 5
1.3.18 | Finned Tube Inspection Visual and dimensional check | 6 |  | 15
1.3.19 | Tube expanding | 2 |  | 5
1.3.20 | PT for tube to tube sheet joint | 0.4 |  | 1
1.4 | Final Inspection | 10 | 10
1.4.1 | Inspection for Completed Tube Bundle | 5 |  | 50
1.4.1.1 | Visual & Dimensional Inspection | 2.5 |  |  | 50
1.4.1.2 | Hydro Test | 2.25 |  |  | 45
1.4.1.3 | Drying , N2 purging | 0.25 |  |  | 5
1.4.2 | Fan and driver assembly inspection | 0.5 |  | 5
1.4.2.1 | Visual & Dimensional Inspection | 0.25 |  |  | 50
1.4.2.2 | Balance test for pulley& belt | 0.1 |  |  | 20
1.4.2.3 | Assembly of rotating parts inspection | 0.05 |  |  | 10
1.4.2.4 | Balance test for fan blades and hubs and Shaft | 0.05 |  |  | 10
1.4.2.5 | Louver visual and dimentional & coating check | 0.05 |  |  | 10
1.4.3 | Electric Motor Inspection | 0.5 |  | 5
1.4.3.1 | Type test | 0.2 |  |  | 40
1.4.3.2 | Routine test | 0.2 |  |  | 40
1.4.3.3 | IP & ExX certificate rewiew | 0.1 |  |  | 20
1.4.4 | Instruments | 0.5 |  | 5
1.4.4.1 | I/P Convertor | 0.225 |  |  | 45
1.4.4.1.1 | Visual inspection | 0.025 |  |  | 5
1.4.4.1.2 | Calibration | 0.025 |  |  | 5
1.4.4.1.3 | IP & ExX certificate rewiew | 0.025 |  |  | 5
1.4.4.2 | Vibration Switch | 0.5 |  |  | 100
1.4.4.2.1 | Visual inspection | 0.4 |  |  |  | 80
1.4.4.2.2 | Test certificate | 0.05 |  |  |  | 10
1.4.4.2.3 | IP & ExX certificate rewiew | 0.05 |  |  |  | 10
1.4.5 | Steel Structure Inspection | 3.5 |  | 35
1.4.5.1 | Material certificate check | 1.75 |  |  | 50
1.4.5.2 | Steel member visual & Dimensional Inspection | 0.7 |  |  | 20
1.4.5.3 | Welding of steel structure | 0.7 |  |  | 20
1.4.5.4 | NDT after welding if any | 0.175 |  |  | 5
1.4.5.5 | Surface Preparation and Painting Inspection (including Side frame, fan ring, plenum, …) | 0.175 |  |  | 5
1.5 | Spare part Inspection | 5 | 5
1.5.1 | Material certificate review | 2.5 |  | 50
1.5.2 | VT, DT, Quantities and packing | 2.5 |  | 50
1.6 | Pre shippment Inspection | 10 | 10
1.6.1 | Prepration for shippment ( shipping mark Check) | 0.4 |  | 4
1.6.2 | Packing and Marking check (Including Packing Condition and Quantity and spare part check) | 0.4 |  | 4
1.6.3 | Touch up and Name plate stamping ( befor attaching) | 0.4 |  | 4
1.6.4 | manufacturer certificate of compliance | 0.4 |  | 4
1.6.5 | Issue Inspection Release Note (IRN) / Shipping Release Note by TPA | 0.2 |  | 2
1.6.6 | Final data book | 3 |  | 30
1.6.7 | IC | 0.2 |  | 2
1.6.8 | SAT | 5 |  | 50