## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-AA-120-PR-CN-0001-V01 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: Thermal Calculation Books |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0008 |  |  | Transmital Date: 2024/08/10
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-AA-120-PR-CN-0001_V01 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بمنظور بررسی طراحی انجام شده و اظهار نظر،ارسال فایل های محاسباتی htri ضروری می باشد |  | PEDCO COMMENTS ON BK-HD-PEDCO-SVTR-AA-0008 | 2024/03/12 | فایل های HTRI به پیوست در دیتا شیت فرآیندی آمده است
2 | فشار طراحی کولر هوایی مرحله اول در مدرک CN-0001 با مدرک DS-0001 تناقض دارد |  | PEDCO COMMENTS ON BK-HD-PEDCO-SVTR-AA-0008 | 2024/03/12 | فشار ورودی براساس آخرین مدرک PFD کارفرما 18 Bar g در نظر گرفته شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Al.Ahmadi | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 2024/03/12 |  |  |  |  | Date: