## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: P&ID |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0020 |  |  | Transmital Date: 2024/10/14
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-AA-120-PR-PI-0001_V00 |  |  | CRS Status: | CM
| Comments (PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Process comments :
1 | مشخصات خط لوله ورودی و خروجی ذکر گردد. |  | BK-SUR-ENG-MEC-03-09471 | 2024-08-19 | اعمال گردید (توضیح اینکه محدوده کاری شرکت آبان از فلنج تافلنج کولرهای هوایی میباشد)
2 | Tie In در ورودیAir Cooler نیز مشخص گردد. |  | BK-SUR-ENG-MEC-03-09471 | 2024-08-19 | اعمال گردید (توضیح اینکه محدوده کاری شرکت آبان از فلنج تافلنج کولرهای هوایی میباشد)
3 | به فايل پيوست مراجه گردد. |  | BK-SUR-ENG-MEC-03-09471 | 2024-08-19 | توضیحات مربوطه در فایل پیوست ارائه شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (PEDCO) |  |  |  |  | EPC Contractor
| Commented By: s.akbari p.paleki | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 19/08/2024 |  |  |  |  | Date: