## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-AA-120-PR-CN-0001-V03 | [5 empty] | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: THERMAL / MECHANICAL CALCULATION BOOK | [5 empty] | PEDCO Tr. No.:BK-HD-PEDCO-SVTR-AA-0029 |  |  | Transmital Date: 2024/11/27
[6 empty] | CRS No:PEDCO-CRS-BK-GCS-AA-120-PR-CN-0001-V03 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date |  | Clarification (By EPC Contractor) |  |  | Client Conclusion
General
1 | 1- مبانی در نظر گرفتن حداقل Rv2 برابر با 1000 برای سایزینگ نازل در سیالات گازی بر اساس چه استاندارد و یا Design practice می باشد؟ |  | BK-SUR-ENG-MEC-03-09622 | 21/Oct/2024 |  | مطابق با توافقات جلسه 14030823 (پیوست)
2 | مبناي انتخاب سرعت سيال در تيوب چيست؟ |  | BK-SUR-ENG-MEC-03-09622 | 21/Oct/2024
3 | با توجه به تاثيرنتايج pulsation study كمپرسور بر روي سايز نازل هاي كولرها، مراتب با شركت هيرگان ميبايستي هماهنگ گردد. |  | BK-SUR-ENG-MEC-03-09622 | 21/Oct/2024
2 | 2- با توجه به ایجاد تغییرات عمده در Duty و سطح و توان فن ها نسبت به ویرایش پیشین (به ویژه در مورد AE-2102 A/B/C) و تایید ذینفع اصلی پروژه در خصوص ویرایش قبل، می بایست داده های اصلی دیتاشیت ویرایش 02 مبنای طراحی قرار گیرد. |  | BK-SUR-ENG-MEC-03-09622 | 21/Oct/2024
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) | [5 empty] | EPC Contractor
| Commented By: Al.Ahmadi | Signature | H.Naserizadeh |  |  |  | Clarified By: | Signature
| Date: 21/Oct/2024 | [5 empty] | Date: