## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: P&ID FOR AIR COOLERS |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0030 |  |  | Transmital Date: 2024/12/02
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-AA-120-PR-PI-0001_V01 |  |  | CRS Status: | CM
| Comments (PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Process comments :
1 | تغییر کلاس در دوسمت کولرهوایی مرحله دوم صحیح نمی باشد. |  | BK-SUR-ENG-MEC-03-09632 | 2024-10-28 | مورد تایید است و اصلاح خواهد شد (هیرگان بایستی تغییر دهد)
2 | مقدار duty کولرها پس از نهایی سازی محاسبات، بر اساس آخرین نتایج تصحیح شود. |  | BK-SUR-ENG-MEC-03-09632 | 2024-10-28 | مورد تایید است و در رویژن بعد اصلاح خواهد شد
3 | نقطه نظرات كارفرما در خصوص موتورها ميبايستي در نظر گرفته شود. |  | BK-SUR-ENG-MEC-03-09632 | 2024-10-28 | پیرو جلسه حضوری مورخ 1403/08/27 و صورت جلسه مذکور قرار نقطه نظرات برق در مدرک مربوطه اعمال خواهد شد.
5 | با توجه به تاثير pulsation study كمپرسور ها بر روي سايزينگ ورودي و خروجي كولرها ، مراتب با شركت هيرگان هماهنگ گردد. |  | BK-SUR-ENG-MEC-03-09632 | 2024-10-28 | مورد بررسی قرار خواهد گرفت
4 | ساير نقطه نظرات در فايل پيوست قيد شده است. |  | BK-SUR-ENG-MEC-03-09632 | 2024-10-28 | TI/PI connection در حوزه کاری آبان می باشد که در نظر گرفته خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.MALEKI | Signature | H.NASERIZADEH |  |  | Clarified By: | Signature
| Date: 28/10/2024 |  |  |  |  | Date: