## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-AA-120-ME-DW-0002 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title:Tube Bundle Drawing |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0021 |  |  | Transmital Date: 2024/11/30
[5 empty] | CRS No:NISOC-CRS-BK-GCS-AA-120-ME-DW-0002_V00 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 03/2294/238538 | 1403/06/25 | با لحاظ نمودن موارد صورتجلسه 14030827 مدرک با وضعیت AFC ارسال می گردد.
2 |  |  | 03/2294/349473 | 1403/09/03 | با لحاظ نمودن موارد صورتجلسه 14030827 مدرک با وضعیت AFC ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Al.Ahmadi | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date:31/Aug/2024 |  |  |  |  | Date: