## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-ME-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: GENERAL ARRANGEMENT DRAWINGS |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0023 |  |  | Transmital Date: 2024/12/01
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-AA-120-ME-DW-0001_V02 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 03/2294/238544 | 1403/06/25 | -
2 | 1 |  |  |  | بر اساس جلسه روز 1403/8/27، پلتفرم ارائه شده در نقشه General Arrangement با عرض 1.2m مورد تائید قرار گرفت.
3 | 2 |  |  |  | در نظر گرفته شده است.
4 | 3 |  |  |  | نمایش داده شد.
5 | 4 |  |  |  | در جلسه مورخ 1403/8/27 این بند منتفی شد.
|  |  | MOM | 1403/08/27 | با لحاظ نمودن موارد صورتجلسه 14030827 مدرک با وضعیت AFC ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Al.Ahmadi | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date:28/Aug/2024 |  |  |  |  | Date: