## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: P&ID FOR AIR COOLERS |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0040 |  |  | Transmital Date: 2025/01/25
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-AA-120-PR-PI-0001_V02 |  |  | CRS Status: | CM
| Comments (PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Process comments :
1 | دما و فشار طراحی کولرها تصحیح گردد. |  | BK-SUR-ENG-MEC-03-09800 | 2024-12-09 | مورد تایید است
2 | با توجه به تاثير pulsation study كمپرسور ها بر روي سايزينگ ورودي و خروجي كولرها ، این اطلاعات می بایست پس از دریافت ااز سازنده کمپرسور، توسط پیمانکار در اختیار شرکت آبان قرار گرفته و به روز رسانی گردد. |  | BK-SUR-ENG-MEC-03-09800 | 2024-12-09 | خواهشمند است این مدرک برای آبان ارسال گردد . همچنین اعلام شود PULSATION STUDY به چه منظور و هدفی در کولر بایستی بررسی گردد .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (PEDCO) |  |  |  |  | EPC Contractor
| Commented By: p.maleki | Signature | h.naserizadeh |  |  | Clarified By: | Signature
| Date: 09/12/2024 |  |  |  |  | Date: