## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-AA-120-PR-CN-0001-V04 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: Thermal/Mechanical Calculation Books |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-AA-0039 |  |  | Transmital Date: 2025/01/27
[5 empty] | CRS No:NISOC-CRS-BK-GCS-AA-120-PR-CN-0001_V04 |  |  | CRS Status: | CM
| Comments (NISOC) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 03/2294/431622 | 1403/10/29 | پاسخ کامنت بخش مکانیک: با توجه به help نرم افزار HTRI، طول تیوب به این صورت تعریف شده است : Tube Bundle:Specifies the total length of tubes in the exchanger bundle, including the unfinned tube length and additional unheated length هم چنین مقدار unfinned tube length نیز به صورت ذیل تعریف شده است: Un-finned Tube length:Specifies the unfinned tube length in the exchanger. Xace uses this value in outside surface area calculations.The effective heat transfer area is calculated using the finned and unfinned tube lengths. در نتیجه و با توجه این تعاریف طول وارد شده در HTRI شامل تمامی بخش ها از جمله بخش های فین نشده و داخل TUBE SHEET نیز می باشد که با نقشه ها مطابقت دارد . شکل موجود در HTRI شماتیک می باشد و این موضوع دلیل بر طول موثر نمی باشد. از آنجایی که در جلسه HELP نرم افزار در دسترس نبود قرار بر این شد که آبان با توجه به تجربه ساخت خود و گارانتی این موضوع را پیش بگیرد. خلاصه دستورالعمل HTRI در صفحه بعد آمده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC) |  |  |  |  | EPC Contractor
| Commented By: Al.Ahmadi P.Maleki | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 13/Dec/2023 |  |  |  |  | Date: