## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-AA-120-QC-PR-0004-V00 | [5 empty] | EPC Contractor Tr. No.:BK-HD-PEDCO-SVTR-AA-0043 |  |  | Transmital Date:2025/04/12
Document Title: surface preparation and painting procedure | [5 empty] | PEDCO Tr. No.: BK-PEDCO-NISOC- |  |  | Transmital Date:
[6 empty] | CRS No:PEDCO-CRS-BK-GCS-AA-120-QC-PR-0004-V00 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date |  | Clarification (By EPC Contractor) |  |  | Client Conclusion
General
1 | نظرات در PDF پیوست ارائه شده است |  | BK-SUR-ENG-QAC-03-09960 | 20/Jan/2025 |  | Will be noted
2 | تامین رنگ از منابع مورد تایید کارفرما و با اخذ گواهینامه شامل دیتاشیت و نتایج تست های آزمایشگاهی انجام شود. |  | BK-SUR-ENG-QAC-03-09960 | 20/Jan/2025 |  | Will be noted
| سیستمهای رنگ مورد استفاده در Air Cooler اپوکسی پلی آمید و پلی اورتان می باشد لذا موارد اضافه از دستورالعمل حذف شود. |  | BK-SUR-ENG-QAC-03-09960 | 20/Jan/2025 |  | Will be noted
3 | در متن دستورالعمل بایستی به شماره استانداردهای مرجع کاربردی اشاره شود. |  | BK-SUR-ENG-QAC-03-09960 | 20/Jan/2025 |  | Will be noted
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) | [5 empty] | EPC Contractor
| Commented By: M.Salimi | Signature | S.Faramarzpour |  |  |  | Clarified By: SH.ZOHARI | Signature
| Date:20/Jan/2025 | [5 empty] | Date: 4.9.2025