## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-BV-320-PM-LI-0001_V00 |  |  |  |  | Vendor Tr. No.: BK-BV-HD-T-0002 |  |  | Transmital Date: 2023/08/09
Document Title: VENDOR PRINT INDEX & SCHEDULE (VPIS) |  |  |  |  | Client Tr. No.: BK-HD-PEDCO-SVTR-BV-0001 |  |  | Transmital Date:2023/08/10
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-BV-320-PM-LI-0001_V00 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | According to related MR and standards, below documents shall be added : |  | BK-SUR-ENG-MEC-02-08179 | 2023-07-26
1.1 | List of spare parts & special tools |  | BK-SUR-ENG-MEC-02-08179 | 2023-07-26 | CONFIRM (Refer to attached VPIS)
1.3 | Packing , Marking & Shipping Procedure |  | BK-SUR-ENG-MEC-02-08179 | 2023-07-26 | CONFIRM (Refer to attached VPIS)
1.4 | Heat treatment procedures |  | BK-SUR-ENG-MEC-02-08179 | 2023-07-26 | CONFIRM (Refer to attached VPIS)
1.5 | welding procedure specification (including repair procedure) |  | BK-SUR-ENG-MEC-02-08179 | 2023-07-26 | CONFIRM (Refer to attached VPIS)
1.6 | As-built drawing |  | BK-SUR-ENG-MEC-02-08179 | 2023-07-26 | NOT CONFIRM اگر در مدرک VPIS شماره مدرکی برای As-built drawing در نظر گرفته شود و تجهیز ساخته شده با آخرین رویژن تایید شده نقشه جنرال تجهیز مغایرتی نداشته باشد (که عدم نیاز به As-built drawing معنی می شود) یک مدرک در VPIS اصطلاحا باز و بدون ارسال باقی می ماند. به طور معمول As-built در صورت نیاز یک رویژن ار نقشه جنرال خواهد بود.
2 | Replace this document on the same Transmittal. |  | BK-SUR-ENG-MEC-02-08179 | 2023-07-26 | CONFIRM
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date:7/26/2023 |  |  |  |  | Date: