## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-BV-320-QC-PR-0003_V01 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title:Surface Preparation and Painting Procedure |  |  |  |  | Tr. No.: BK-HD-PEDCO-SVTR-BV-0003 |  |  | Transmital Date:2023/11/15
[5 empty] | CRS No:NISOC-CRS-BK-PPL-BV-320-QC-PR-0003_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02-2294-255066 | 1402/06/30 | موارد کلی : مورد1- مسولیت تهیه این مدارک و تضمین کیفیت ساخت به عهده شرکت ویستا می باشد. مورد2- تمامی الزامات استاندارد IPS-M-PI-130 برای کالا در نظر گرفته شده است. مورد3 -الزامات Anne H استاندارد IPS-M-PI-190 و API 5L بر روی قسمتهای ساخته شده از لوله در نظر گرفته خواهد شد.
2 |  |  |  |  | مورد1- تغییر فام رنگ لایه میانی انجام شد. (RAL 1014)
3 |  |  |  |  | مورد2- بازنگری عنوان استاندارد ها انجام شد.
4 |  |  |  |  | مورد3-ابعاد ساینده مسباره اصلاح شد.
5 |  |  |  |  | مورد4- دیتاشیت سه لایه رنگ مورد استفاده در مدرک ارایه شده است.
6 |  |  |  |  | مورد5- الزام انجام آزمون گرد و غبار در مدرک آورده شد.
7 |  |  |  |  | مورد6- استفاده از روش Airless به عنوان روش اصلی در مدرک آورده شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 20-Sep-2023 |  |  |  |  | Date: