## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-BV-320-QC-PR-0003_V00 |  |  |  |  | EPC Contractor Tr. No. |  |  | Transmital Date
Document Title: Surface Preparation and Painting Procedure |  |  |  |  | Tr. No.: :BK-HD-PEDCO-SVTR-BV-0003 |  |  | Transmital Date:2023/11/18
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-BV-320-QC-PR-0003_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرك متناسب با شرايط واقعي تجهيز و الزامات SPEC پروژه تهيه نشده و بسياري موارد درج شده در آن نا مرتبط ميباشد. لازم است مدرك بطور اختصاصي براي تجهيز مورد نظر با در نظر گرفتن الزامات مدرك Specification for Painting به شماره مدرك BK-GNRAL-PEDCO-000-PI-SP-0006-D04 بطور كلي اصلاح گردد. |  | BK-SUR-ENG-QAC-02-08503 | 20 -Sep-2023 | مدرک ارایه شده شامل تمامی موارد مهم و مطابق استاندارد جهت آماده سازی سطح و رنگ آمیزی تجهیز لانچر و رسیور می باشد که در پروژه های مشابه با کارفرمای مناطق نفت خیز جنوب مورد تایید بوده است و یا کامنتهای مختصری (مشابه کامنت های فعلی مناطق) داشته است. ضمن اینکه الزامات Specification for Painting به شماره مدرك BK-GNRAL-PEDCO-000-PI-SP-0006-D04 نیز رعایت شده است. لطفا نقطه نظرات خود را به تفکیک و قابل ارجاع بیان فرمایید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 20-Sep-2023 |  |  |  |  | Date: