## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-BV-320-QC-PR-0004_V01 |  |  |  |  | EPC Contractor Tr. No. |  |  | Transmital Date:
Document Title: NDE Procedure |  |  |  |  | Tr. No.: BK-HD-PEDCO-SVTR-BV-0003 |  |  | Transmital Date:2023/11/18
[5 empty] | CRS No: NISOC-CRS-BK-PPL-BV-320-QC-PR-0004_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02-2294-255066 | 1402/06/30 | موارد کلی : مورد1- مسولیت تهیه این مدارک و تضمین کیفیت ساخت به عهده شرکت ویستا می باشد. مورد2- تمامی الزامات استاندارد IPS-M-PI-130 برای کالا در نظر گرفته شده است. مورد3 -الزامات Anne H استاندارد IPS-M-PI-190 و API 5L بر روی قسمتهای ساخته شده از لوله در نظر گرفته خواهد شد.
2 | تهیه دستورالعمل انجام آزمون های غیر مخرب می بایست توسط کارخانه سازنده و با تایید یک بازرس دارای صلاحیت سطح 3 صورت پذیرد. لذا در این خصوص اظهار نظر پس از تایید بازرس آزمون های غیر مخرب با سطح 3 انجام خواهد پذیرفت. |  | 02-2294-255066 | 1402/06/30 | الزام تایید دستورالعمل آزمون های غیر مخرب توسط بازرس با سطح سه در مدرک آورده شده و تایید خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 20-Sep-2023 |  |  |  |  | Date: