## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-BV-320-QC-PR-0004_V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date
Document Title: NDE Procedure |  |  |  |  | Tr. No.: BK-HD-PEDCO-SVTR-BV-0003 |  |  | Transmital Date:2023/11/18
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-BV-320-QC-PR-0004_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند Definition اضافه شده و در آن تعريف مربوط به پروژه و كليه ذينفعان (Venor, EPC Contractor, EPCD Contractor, TPI ,Client) آورده شود. |  | BK-SUR-ENG-QAC-02-08503 | 20 -Sep-2023 | انجام شد.
2 | مدرك بايد به تاييد بازرس داراي گواهينامه Level III رسيده و توسط ايشان مهر و امضا گردد. |  | BK-SUR-ENG-QAC-02-08503 | 20 -Sep-2023 | مدرک اصلاح شد.
3 | نوع و درصد انجام تست NDT بر اساس مدرك Weld and NDT Map اصلاح گردد. |  | BK-SUR-ENG-QAC-02-08503 | 20 -Sep-2023 | در مدرک Weld & NDT Map الزام انجام تست به تفکیک روی هر خط جوش (100%) بیان شده است و در مدرک NDE Procedure روش انجام تست های غیر مخرب آورده شده است.
4 | فرمت Dimension Test از انتهاي مدرك حذف گردد. |  | BK-SUR-ENG-QAC-02-08503 | 20 -Sep-2023 | انجام شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 20-Sep-2023 |  |  |  |  | Date: