## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-BV-320-QC-PR-0009-V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date
Document Title: Packing, Marking and Shipping Procedure |  |  |  |  | Tr. No.: :BK-HD-PEDCO-SVTR-BV-0003 |  |  | Transmital Date:2023/11/18
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-BV-320-QC-PR-0009-V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 2 : -نام و ويرايش استانداردهاي مرجع درج گردد. -مدرك SR-00-MK-000-GE-SP-0001-D00 جزء مدارك پروژه نميباشد. - مدرك PACKING , MARKING , TRANSPORTATION PROCEDURE به شماره BK-GNRAL-PEDCO-000-QC-PR-0045-D00 به عنوان مرجع در نظر گرفته شده و الزامات آن در مدرك لحاظ گردد. |  | BK-SUR-ENG-QAC-02-08503 | 19-Sep-2023 | انجام شد.
2 | شماره رديف هاي ليست شده در Table Of content با شماره هاي موجود در متن دستورالعمل مطابقت ندارد . |  | BK-SUR-ENG-QAC-02-08503 | 19-Sep-2023 | اصلاح شد.
3 | در فرم Packing List محل امضاي كليه ذينفعان در نظر گرفته شود. |  | BK-SUR-ENG-QAC-02-08503 | 19-Sep-2023 | انجام شد.
4 | ساير نقطه نظرات روي مدرك درج گرديده است. |  | BK-SUR-ENG-QAC-02-08503 | 19-Sep-2023 | انجام شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 19-Sep-2023 |  |  |  |  | Date: