## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-BV-320-ME-CN-0001-V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: Mechanical Calculation Book for Pig Launcher Trap (PL-3201) |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-BV-0002 |  |  | Transmital Date:2023/12/20
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-BV-320-ME-CN-0001_V00 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | محاسبات WRC نازل ها و lifting lug ميبايستي به مدرك اضافه گردد. |  | BK-SUR-ENG-MEC-02-08363 | 2023-08-30 | نیروها و ممان هر نازل توسط واحد Piping پروژه به سازنده اعلام شودتا در محاسبات اعمال گردد.
2 | سرعت مبناي باد پرو‍ژه بينك بر طبق آيين نامه بارگذاري ايران سال 1398 برابر 120km/h مي باشد وميبايستي بر اساس ضرايب تبديل به سرعت مبناي باد -ASCE-7- 2010 تبديل گردد. سرعت 232km/h اشاره شده با فرض ضريب اهميت يك محاسبه گرديده است. . موارد مطرح شده در فايل پيوست به عنوان نمونه ذكر شده، لذا در مابقي مدارك نيز اعمال گردند. |  | BK-SUR-ENG-MEC-02-08363 | 2023-08-30 | انجام شد.
3 | با توجه به گزارش مكانيك خاك و مقدار سرعت موج برشي، تيپ خاك II مي باشد لذا پارامترهاي لرزه اي 2800 به شرح ذيل مي باشند: تبديل پارامترهاي آيين نامه 2800 به ASCE7-2010 با روش سعي وخطا كه مي توانند با مسووليت پيمانكار مورد استفاده قرار گيرند: Site Classification = C & SS =1.125 & S1=0.46 & Fa= 1 & Fv= 1.33 و Seismic Design Category=D |  | BK-SUR-ENG-MEC-02-08363 | 2023-08-30 | انجام شد.
4 | در خصوص آيتم هاي 2و3 قبلا با بخش سازه پيمانكار توافق شده است. |  | BK-SUR-ENG-MEC-02-08363 | 2023-08-30
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 08/30/2023 |  |  |  |  | Date: