## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-BV-320-ME-DW-0003-V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: General Drawing for Pig Launcher Trap (PR-3201) |  |  |  |  | Tr. No.:BK-HD-PEDCO-SVTR-BV-0002 |  |  | Transmital Date:2023/12/20
[5 empty] | CRS No:NISOC-CRS-BK-PPL-BV-320-ME-DW-0003_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02-2294-340430 | 1402/08/24 | 1- تمامی الزامات استاندارد IPS-M-PI-130 برای کالا در نظر گرفته شده است. همچنین الزامات Anne H استاندارد IPS-M-PI-190 و API 5L بر روی قسمتهای ساخته شده از لوله در نظر گرفته خواهد شد. 2- این داده ها بر اساس ردیف 15 دیتاشیت پروژه می باشد ضمن اینکه محاسبات نیروی باد در نرم افزار PV Elite-2019 انجام شده و آخرین رویژن استانداردASCE در این نرم افزار 2010 می باشد. 3- رجوع شود به IPS-M-PI-130-5.2.3، استانداردهای ASME B31.8 و ASME B31.4 جهت طراحی قطعات تحت فشار عنوان شده است که در این استاندارد ها فشار طراحی (Design Pressure) -مطابق با دیتاشیت پروژه ردیف 13- مبنای طراحی قطعات تحت فشار است. 4- انجام شد. 5- به پیوست آمده است. 6- انجام شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 20-Sep-2023 |  |  |  |  | Date: