## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-BV-320-ME-DW-0003-V01 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: General Drawing for Pig Launcher Trap (PR-3201) |  |  |  |  | Tr. No.:BK-HD-PEDCO-SVTR-BV-0008 |  |  | Transmital Date:20203/05
[5 empty] | CRS No:NISOC-CRS-BK-PPL-BV-320-ME-DW-0003_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02-2294-432514 | 1402/10/23 | اصلاحات موردنظر اعمال گردید.
2 |  |  | 02-2294-432514 | 1402/10/23 | با توجه به تطابق کامل لوله ها با نیازمندی های سرویس ترش و استاندارد NACE-MR0175 ، لطفا در صورت امکان، نقطه نظر مطروحه بازنگری گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 20-Sep-2023 |  |  |  |  | Date: