## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-BV-320-ME-DW-0004-V01 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: General Drawing for Pig Receiver Trap (PR-3201) |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-BV-0008 |  |  | Transmital Date:2024/03/05
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-BV-320-ME-DW-0004_V01 |  |  | CRS Status: | CM
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Basic wind speed (ASCE-7 2010) = 232 km/h Basic wind speed (INBC 1398) = 120 km/h |  | BK-SUR-ENG-MEC-02-08926 | 2024-01-03 | Basic wind speed طبق (ASCE-2010) مقدار 232km/h اصلاح شد.
1 | Quick opening detail shall be added. Nozzle detail shall be added. Lifting lug detail shall be added. Detail for earth connection shall be added. |  | BK-SUR-ENG-MEC-02-08926 | 2024-01-03 | در مدرک VPIS ، فقط نقشه ی جنرال و name plate خوسته شده است و Detail مربوط به Q.O.C , Nozzle , Lifting Lug و earth connection ذکر نشده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 01/03/2024 |  |  |  |  | Date: