## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-BV-320-QC-PR-0001_V01 |  |  |  |  | EPC Tr./ Letter No.: BK-HD-PEDCO-SVTR-BV-0006 |  |  | Tr.Letterl Date:
Document Title :INSPECTION & TEST PLAN (ITP) |  |  |  |  | PEDCO Tr. No: BK-HD-PEDCO-SVTR-BV-0006 |  |  | Transmital Date: 2024/04/28
[5 empty] | CRS No:PEDCO-CRS-BK-PPL-BV-320-QC-PR-0001_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بندهای 19 و 20 صورتجلسه PIM که بصورت دست نویس بعد از امضای نمایندگان پترو ایران و NISOC به صورتجلسه اضافه شده است مورد تایید این شرکت نمی باشد. |  | س ط ب/7520 | 2024-07-22 | متریال مورد استفاده منطبق بر نیازمندی های سرویس ترش بوده و گواهینامه اصل ارائه خواهد شد.
2 | كليه نقطه نظرات روي مدرك درج گرديده است. |  |  | 11.04.2023 | موارد مطروحه به نحو مقتضی اعمال گردید.
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: 11.04.2023 |  |  |  |  | Date: 24/08/2021