## Cover
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج های کمپرسور گاز (رفت و برگشتی) بینک (قرارداد BK-HD-GCS-CO-0008_03)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه |  | بسته کاری | صادرکننده | تسهیلات |  | رشته | نوع مدرک | سریال | نسخه |  | شماره صفحه: 1 از 4
9184 – 073 - 053 |  |  | BK |  | GCS | HY | 120 |  | PM | LI | 0001 | V03
طرح نگهداشت و افزایش تولید 27 مخزن
VENDOR PRINT INDEX & SCHEDULE (VPIS) نگهداشت و افزایش تولید میدان نفتی بینک
V03 |  | AUG.2023 |  | IFR |  |  |  | Havayar Co. |  |  | M.Fakharian |  | A.M.Mohseni
V02 |  | APR.2023 |  | IFR |  |  |  | Havayar Co. |  |  | M.Fakharian |  | M.Mehrshad
V01 |  | MAR.2023 |  | IFR |  |  |  | Havayar Co. |  |  | M.Fakharian |  | M.Mehrshad
V00 |  | JAN.2023 |  | IFR |  |  |  | Havayar Co. |  |  | M.Fakharian |  | M.Mehrshad
Rev. |  | Date |  | Purpose of Issue / Status |  |  |  | Prepared by: |  |  | Checked by: |  | Approved by: |  | CLIENT Approval
CLIENT Doc. Number:
status:
IFR: Issued For Review
IFR: Issued For Review
IFI: Issued For Information
AFC: Approved For Construction

## REVISION
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج های کمپرسور گاز (رفت و برگشتی) بینک (قرارداد BK-HD-GCS-CO-0008_03)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  |  | پروژه | بسته کاری |  | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال |  | نسخه |  | شماره صفحه: 2 از 4
9184 – 073 - 053 |  |  | BK | GCS |  | HY | 120 | PM | LI | 0001 |  | V03
REVISION RECORD SHEET
Page | V00 | V01 | V02 |  | V03 |  | V04 |  | Page |  | V00 |  | V01 |  | V02 | V03 | V04
1 | X | X | X |  | X |  |  |  | 65
2 | X | X | X |  | X |  |  |  | 66
3 | X | X | X |  | X |  |  |  | 67
4 | X | X | X |  | X |  |  |  | 68
5 | [8 empty] | 69
6 | [8 empty] | 70
7 | [8 empty] | 71
8 | [8 empty] | 72
9 | [8 empty] | 73
10 | [8 empty] | 74
11 | [8 empty] | 75
12 | [8 empty] | 76
13 | [8 empty] | 77
14 | [8 empty] | 78
15 | [8 empty] | 79
16 | [8 empty] | 80
17 | [8 empty] | 81
18 | [8 empty] | 82
19 | [8 empty] | 83
20 | [8 empty] | 84
21 | [8 empty] | 85
22 | [8 empty] | 86
23 | [8 empty] | 87
24 | [8 empty] | 88
25 | [8 empty] | 89
26 | [8 empty] | 90
27 | [8 empty] | 91
28 | [8 empty] | 92
29 | [8 empty] | 93
30 | [8 empty] | 94
31 | [8 empty] | 95
32 | [8 empty] | 96
33 | [8 empty] | 97
34 | [8 empty] | 98
35 | [8 empty] | 99
36 | [8 empty] | 100
37 | [8 empty] | 101
38 | [8 empty] | 102
39 | [8 empty] | 103
40 | [8 empty] | 104
41 | [8 empty] | 105
42 | [8 empty] | 106
43 | [8 empty] | 107
44 | [8 empty] | 108
45 | [8 empty] | 109
46 | [8 empty] | 110
47 | [8 empty] | 111
48 | [8 empty] | 112
49 | [8 empty] | 113
50 | [8 empty] | 114
51 | [8 empty] | 115
52 | [8 empty] | 116
53 | [8 empty] | 117
54 | [8 empty] | 118
55 | [8 empty] | 119
56 | [8 empty] | 120
57 | [8 empty] | 121
58 | [8 empty] | 122
59 | [8 empty] | 123
60 | [8 empty] | 124
61 | [8 empty] | 125
62 | [8 empty] | 126
63 | [8 empty] | 127
64 | [8 empty] | 128

## VPIS
نگهداشت و افزایش تولید میدان نفتی بینک سطح الارض و ابنیه تحت الارض
خرید پکیج های کمپرسور گاز (رفت و برگشتی) بینک (قرارداد BK-HD-GCS-CO-0008_03)
VENDOR PRINT INDEX & SCHEDULE (VPIS)
شماره پیمان: |  | پروژه | بسته کاری | صادرکننده | تسهیلات | رشته | نوع مدرک | سریال | نسخه | شماره صفحه: از
9184 – 073 - 053 |  | BK | GCS | HY | 120 | PM | LI | 0001 | V03
S/R No. | Doc. No. | Document Description | [7 empty] | Scope | Status | Remarks
1 | General/ Management
1.1 | List
1.1.1 | BK-GCS-HY-120-PM-LI-0001 | VENDOR PRINT INDEX & SCHEDULE (VPIS) | [7 empty] | NISOC | IFR
1.1.2 | BK-GCS-HY-120-GE-WB-0001 | WORK BREAKDOWN STRUCTURE | [7 empty] | NISOC | IFR
1.1.3 | BK-GCS-HY-120-GE-VL-0001 | SUB VENDOR LIST | [7 empty] | NISOC | IFR
1.1.4 | BK-GCS-HY-120-GE-SH-0001 | TIME SCHEDULE | [7 empty] | NISOC | IFR
1.1.5 | BK-GCS-HY-120-GE-LI-0002 | SPARE PART LIST | [7 empty] | NISOC | IFR
1.1.6 | BK-GCS-HY-120-GE-LI-0003 | FINAL DATA BOOK INDEX | [7 empty] | NISOC | IFR
1.1.7 | BK-GCS-HY-120-GE-LI-0004 | PACKING LIST | [7 empty] | NISOC | IFA
1.1.9 | BK-GCS-HY-120-GE-WB-0001 | WORK BREAKDOWN STRUCTURE | [7 empty] | NISOC | IFR
1.1.10 | BK-GCS-HY-120-GE-VL-0001 | SUB VENDOR LIST | [7 empty] | NISOC | IFR
1.1.11 | BK-GCS-HY-120-GE-SH-0001 | TIME SCHEDULE | [7 empty] | NISOC | IFR
1.2 | Drawing/Diagram
1.2.1 | BK-GCS-HY-120-GE-DW-0001 | NAME PLATE DRAWING | [7 empty] | NISOC | IFR
1.3 | Reports
1.3.1 | BK-GCS-HY-120-GE-DO-0001 | FINAL DATA BOOK | [7 empty] | NISOC | IFA
2 | QA/QC
2.1 | Procedure/Plan
2.1.1 | BK-GCS-HY-120-QC-PR-0001 | INSPECTION & TEST PLAN (ITP) | [7 empty] | NISOC | IFA
2.1.2 | BK-GCS-HY-120-QC-PR-0002 | W.P.S & P.Q.R | [7 empty] | NISOC | IFR
2.1.3 | BK-GCS-HY-120-QC-PR-0003 | SURFACE PREPARATION AND PAINTING PROCEDURE | [7 empty] | NISOC | IFR
2.1.4 | BK-GCS-HY-120-QC-PR-0004 | NDE PROCEDURE | [7 empty] | NISOC | IFR
2.1.5 | BK-GCS-HY-120-QC-PR-0005 | HYDROSTATIC/ PNEUMATIC TEST PROCEDURE | [7 empty] | NISOC | IFR
2.1.6 | BK-GCS-HY-120-QC-PR-0006 | SAT (PERFORMANCE TEST) PROCEDURE | [7 empty] | NISOC | IFR
2.1.7 | BK-GCS-HY-120-QC-PR-0007 | FAT PROCEDURE | [7 empty] | NISOC | IFR
2.2 | Manual
2.2.1 | BK-GCS-HY-120-QC-ML-0001 | INSTALLATION, OPERATION & MAINTENANCE MANUAL | [7 empty] | NISOC | IFR
3 | Process
3.1 | Calculation
3.1.1 | BK-GCS-HY-120-PR-CN-0001 | CALCULATION NOTE FOR PSV SIZING | [7 empty] | NISOC | IFR
3.1.2 | BK-GCS-HY-120-PR-CN-0002 | CALCULATION NOTE FOR CONTROL VALVE SIZING | [7 empty] | NISOC | IFR
3.2 | Philosophy
3.2.1 | BK-GCS-HY-120-PR-PH-0001 | CONTROL PHILOSOPHY | [7 empty] | NISOC | IFR
3.3 | Drawing/Diagram
3.3.1 | BK-GCS-HY-120-PR-PF-0001 | PFD | [7 empty] | NISOC | IFI
3.3.2 | BK-GCS-HY-120-PR-PI-0001 | P&I D | [7 empty] | NISOC | IFR
3.4 | List
3.4.1 | BK-GCS-HY-120-PR-LI-0001 | UTILITY CONSUMPTION LIST | [7 empty] | NISOC | IFR
3.4.2 | BK-GCS-HY-120-PR-LI-0002 | EQUIPMENT LIST | [7 empty] | NISOC | IFR
4 | Mechanical
4.1 | Drawing/Diagram
4.1.1 | BK-GCS-HY-120-ME-DW-0001 | COMPRESSOR PACKAGE GENERAL ARRANGEMENT DRAWING | [7 empty] | NISOC | IFR
4.1.2 | BK-GCS-HY-120-ME-DW-0002 | SHAFT COUPLING ASSEMBLY DRAWING AND BILL OF MATERIAL | [7 empty] | NISOC | IFI
4.1.3 | BK-GCS-HY-120-ME-DW-0003 | CROSS SECTIONAL DRAWING | [7 empty] | NISOC | IFR
4.2 | Datasheet
4.2.1 | BK-GCS-HY-120-ME-DS-0001 | DETAILED D/SH FOR COMPRESSOR (API-618) WITH CERTIFICATES | [7 empty] | NISOC | IFR
5 | Instrument
5.1 | Datasheet
5.1.1 | BK-GCS-HY-120-IN-DS-0001 | INSTRUMENT DATASHEETS / CERTIFICATES | [7 empty] | NISOC | IFR
5.1.2 | BK-GCS-HY-120-IN-DS-0002 | DATASHEET FOR CONTROL/REGULATOR VALVES | [7 empty] | NISOC | IFR
5.1.3 | BK-GCS-HY-120-IN-DS-0003 | DATASHEET FOR ON/OFF VALVES (IF ANY) | [7 empty] | NISOC | IFR
5.1.4 | BK-GCS-HY-120-IN-DS-0004 | DATASHEET FOR SAFETY VALVES | [7 empty] | NISOC | IFR
5.1.5 | BK-GCS-HY-120-IN-DS-0005 | CONTROL PANEL PARTS DATA SHEET/LICENCE LIST/ CERTIFICATES | [7 empty] | NISOC | IFR
5.2 | List
5.2.1 | BK-GCS-HY-120-IN-LI-0001 | CAUSE & EFFECT CHARTS LIST | [7 empty] | NISOC | IFR
5.2.2 | BK-GCS-HY-120-IN-LI-0002 | INSTRUMENT/F&G LIST | [7 empty] | NISOC | IFR
5.2.3 | BK-GCS-HY-120-IN-LI-0003 | INSTRUMENT CABLE LIST | [7 empty] | NISOC | IFR
5.2.4 | BK-GCS-HY-120-IN-LI-0004 | ALARM & SET POINT LIST | [7 empty] | NISOC | IFR
5.2.5 | BK-GCS-HY-120-IN-LI-0005 | I/O List | [7 empty] | NISOC | IFR
5.3 | Drawing/Diagram
5.3.1 | BK-GCS-HY-120-IN-DW-0001 | HMI AND GRAPHICS PRINTOUT | [7 empty] | NISOC | IFR
5.3.2 | BK-GCS-HY-120-IN-DW-0002 | CONTROL SYSTEM CABINETS AND CONSOLES LAYOUT DRAWING | [7 empty] | NISOC | IFR
5.3.3 | BK-GCS-HY-120-IN-DW-0003 | JB TERMINATION DRAWING | [7 empty] | NISOC | IFR
5.3.4 | BK-GCS-HY-120-IN-DW-0004 | INSTRUMENT EARTH DISTRIBUTION DIAGRAM | [7 empty] | NISOC | IFR
5.3.5 | BK-GCS-HY-120-IN-DW-0005 | CP CONTROL AND SAFETY LOOP DIAGRAM | [7 empty] | NISOC | IFR
5.3.6 | BK-GCS-HY-120-IN-DW-0006 | UCP CONTROL AND SAFETY LOGIC DIAGRAM | [7 empty] | NISOC | IFR
5.3.7 | BK-GCS-HY-120-IN-DW-0007 | HOOK UP DRAWING | [7 empty] | NISOC | IFR
5.3.8 | BK-GCS-HY-120-IN-DG-0001 | PLC WIRING DIAGRAM & TERMINAL DETAILS | [7 empty] | NISOC | IFR
5.3.9 | BK-GCS-HY-120-IN-DG-0002 | OVERAL CONTROL/SAFETY SYSTEM CONFIGURATION DIAGRAM | [7 empty] | NISOC | IFR
5.3.10 | BK-GCS-HY-120-IN-PY-0001 | LCP AND GAUGE BOARD LAYOUT | [7 empty] | NISOC | IFR
5.3.11 | BK-GCS-HY-120-IN-PY-0002 | INSTRUMENT CABLE ROUTE/ MAIN TUBING LAYOUT DRAWING | [7 empty] | NISOC | IFR
5.4 | Procedure/Plan
5.4.1 | BK-GCS-HY-120-IN-PR-0001 | SAT (PERFORMANCE TEST) PROCEDURE FOR CONTROL SYSTEM | [7 empty] | NISOC | IFR
5.4.2 | BK-GCS-HY-120-IN-PR-0002 | FAT PROCEDURE FOR CONTROL SYSTEM | [7 empty] | NISOC | IFR
6 | Electrical
6.1 | Datasheet
6.1.1 | BK-GCS-HY-120-EL-DS-0001 | D/SH (W/CURVE, DRAWING & CERTIFICATE) FOR COMPRESSOR MAIN MOTOR | [7 empty] | NISOC | IFR
6.1.2 | BK-GCS-HY-120-EL-DS-0002 | DATASHEET (W/DRAWING) FOR AUXILIARY MOTORS | [7 empty] | NISOC | IFR
6.2 | Drawing/Diagram
6.2.1 | BK-GCS-HY-120-EL-DW-0001 | ELECTRICAL WIRING DIAGRAM AND CABLE LIST | [7 empty] | NISOC | IFI
6.3 | List
6.3.1 | BK-GCS-HY-120-EL-LI-0001 | ELECTRICAL/UPS CONSUMPTION LOAD LIST | [7 empty] | NISOC | IFR
Notes: 1 : Final Status of documents with status of "IFR" & "IFA" will be "AFC".