## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-IN-LI-0002_V01
Document Title:INSTRUMENT/F&G LIST |  |  |  |  | PEDCO Tr. No.:BK-HD-PEDCO-SVTR-HY-0004 |  |  | Transmital Date:2023/08/28
[5 empty] | CRS No:NISOC-CRS-BK-GCS-HY-120-IN-LI-0002_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument comments :
1 | مدارک مرجع درج گردد. |  | 02/2294/123984 | 1402/03/31 | این مورد در ویرایش قبلی نیز لحاظ شده بود (ستون مربوط به شماره P&ID ) |  | انجام گردید
2 | تجهیزات F&G مشاهده نگردید ، چرا عنوان مدرک شامل F&G می باشد |  | 02/2294/123984 | 1402/03/31 | مورد تایید است.
3 | در ستون Tag Number:تجهیرات مربوط به هر ردیف کمپرسور در ردیف جداگانه ذکر شود و از آوردن عبارت A/B/C بصورت مشترک خودداری شود این موضوع برای دیگر ستونها و ردیفها نیز رعایت گردد. |  | 02/2294/123984 | 1402/03/31 | مورد تایید است.
4 | در ستونLCP,UCp ,System هر ردیف کمپرسور بصورت مشخص نمایش داده شود. |  | 02/2294/123984 | 1402/03/31 | مورد تایید است.
5 | این مدرک پس از نهایی سازی نقشه های P&IDو دیگر مدارک سازنده بروز رسانی گردد. |  | 02/2294/123984 | 1402/03/31 | براساس آخرین P&D به روز شده است.
6 | در خصوص موارد Hold توضیح داده شود. |  | 02/2294/123984 | 1402/03/31 | در رویژن بعد ارسال تکمیل می گردد
Process comments :
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 17 Jul 2023 |  |  |  |  | Date: