## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-EL-DS-0002_V00 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: Datasheet (W/Drawing) For Auxiliary Motors |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-HY-0012 |  |  | Transmital Date:2023/10/14
[5 empty] | CRS No: NISOC-CRS-BK-GCS-HY-120-EL-DS-0002_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | صفحات 7/26 & 5/26: اطلاعات مورد نیاز در ردیف‌های 31 و 32 میبایست توسط سازنده، تکمیل گردد. |  | 02/2294/209277 | 1402/05/28 | تکمیل گردید.
2 | مدرک مذکور می‌بایست پس از تکمیل، ممهور به مهر سازنده جهت بررسی به این امور ارسال گردد. |  | 02/2294/209277 | 1402/05/28 | دیتاشیت ارسالی با توجه به شرایط تحریمی امکان ممهور شدن به مهر سازنده را ندارد ولی در فاینال بوک ارائه خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: