## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-ME-DS-0001-V01
Document Title: DETAILED D/SH FOR COMPRESSOR (API-618) WITH CERTIFICATES |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-HY-0011 |  |  |  | Transmital Date:2023/10/14
|  |  |  | CRS No:NISOC-CRS- BK-GCS-HY-120-ME-DS-0001-V01 |  |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02/2294/218743 | 1402/06/04 | مورد تایید است
|  |  | 02/2294/218743 | 1402/06/04 | Except rod drop. Not to be added.
2 |  |  | 02/2294/218743 | 1402/06/04 | امکان پذیر نمی باشد مدرک موتور آماده نمی باشد .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M. Mahdavi | Signature
| Date: |  |  |  |  | Date: 2023 / 06 / 21