## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-PR-LI-0002_V00
Document Title: EQUIPMENT LIST |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-HY-0001 |  |  | Transmital Date:2023/10/30
[5 empty] | CRS No: CRS-BK-GCS-HY-120-PR-LI-0002-V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فشار طراحی تجهیزات مرتبط با کمپرسور مرحله اول، 24.5 بار درج شده است در حالیکه این عدد در مدارک پروژه 22 بار می باشد. ضروریست این عدم تطابق بر اساس محاسبات دقیق فشار Settleout مرتفع گردد. |  | BK-SUR-ENG-PCS-02-07606 | 2023-05-17 | HAVAYAR: The recommendation of HAVAYAR is 24.5 barg. Any change in this item is not HAVAYAR's Responsibility.
2 | كليه تجهيزات مكانيكال از جمله سيستم Lubricator و Oil Tank همراه با مشخصات كلي و Tag No. به ليست اضافه گردد. |  | BK-SUR-ENG-PCS-02-07606 | 2023-05-17 | HAVAYAR: The required changes will be applied.
3 | نظرات ذینفع اصلی پروژه متعاقبا ارسال می گردد. |  | BK-SUR-ENG-PCS-02-07606 | 2023-05-17 | HAVAYAR: The required changes will be applied.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 17 May 2023 |  |  |  |  | Date: