## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-HY-120-IN-DS-0001
Document Title:INSTRUMENT DATASHEETS / CERTIFICATES |  |  |  |  | PEDCO Tr. No.::BK-HD-PEDCO-SVTR-HY-0027 |  |  | Transmital Date: 2023/11/05
[5 empty] | CRS No:NISOC-CRS-BK-GCS-HY-120-IN-DS-0001_V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument comments :
1 |  |  | 02/2294/306488 | 1402/08/03 | مورد تایید است.
2 |  |  | 02/2294/306488 | 1402/08/03 | مورد تایید است. اصلاح می شود
3 |  |  | 02/2294/306488 | 1402/08/03 | برای ترموول مورد تایید است.
4 |  |  | 02/2294/306488 | 1402/08/03 | مورد تایید است. برای فشار و دما و فلو
5 |  |  | 02/2294/306488 | 1402/08/03 | مورد تایید است.
6 |  |  | 02/2294/306488 | 1402/08/03 | مورد تایید است. اصلاح می شود
7 |  |  | 02/2294/306488 | 1402/08/03 | مورد تایید است.
8 |  |  | 02/2294/306488 | 1402/08/03 | برای Flow indicator خط نیتروژن و Sight glass خط آب امکان پذیر نیست و کلاس 150 استفاده می گردد. خطوط آب کلاس 150 استفاده می شود.
Process comments :
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 17 Jul 2023 |  |  |  |  | Date: