## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-IN-DS-0004 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-HY-0029 |  |  | Transmital Date: 2023/10/01
Document Title: DATASHEET FOR SAFETY VALVES |  |  |  |  | Client Tr. No: |  |  | Transmital Date:
[5 empty] | CRS No:PECO- CRS-BK-GCS-HY-120-IN-DS-0004-V00 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به Block Outlet بودن سناریوی سایزینگ PSV_2192 و PSV_2193 ( لحاظ 10درصد Overpressure factor ) این PSVها میبایست با یک یدک در P&ID نمایش داده شود و در مدرک Data Sheet ارسالی نیز این مساله لحاظ گردد. |  | BK-SUR-ENG-MEC-02-08613 | 2023-10-17 | .
2 | در مدرک ارسالی Orifice designation مربوط به PSV های خروجی کمپرسورها مشخص نشده است. |  | BK-SUR-ENG-MEC-02-08613 | 2023-10-17
3 | دانسیته مربوط به PSV-2204 بازبینی گردد |  | BK-SUR-ENG-MEC-02-08613 | 2023-10-17
4 | شماره تگ بعضي از PSVها در P&ID ها مشخص نمي باشد |  | BK-SUR-ENG-MEC-02-08613 | 2023-10-17
5 | در تمامي ديتاشيت ها بايستي شماره صفحه مربوطه در P&ID مشخص گردد. |  | BK-SUR-ENG-MEC-02-08613 | 2023-10-17
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 10/17/2023 |  |  |  |  | Date: