## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-QC-PR-0004 |  |  |  |  | EPC Contractor Tr. No.: |  |  | Transmital Date:
Document Title: NDE PROCEDURE |  |  |  |  | PEDCO Tr. No.: BK-HD-PEDCO-SVTR-HY-0002 |  |  | Transmital Date:2023/11/06
[5 empty] | CRS No: NISOC-CRS-BK-GCS-HY-120-QC-PR-0004-V00 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (Vendor) |  |  | Client Conclusion
1 | در استانداردهای مرجع، استاندارد API618 نیز ذکر گردد و مدرک در صورت نیاز بر این اساس اصلاح گردد. |  | 02/2294/282356 | 1402/07/18 | Noted
2 | در این مدرک می بایست به تایید بازرس غیر مخرب با سطح 3 رسانیده شود و تاییدیه آن به رویت و بازبینی بازرس شخص ثالث پروژه برسد. |  | 02/2294/282356 | 1402/07/18 | 13-5-2-9 بند IPS-C-PI-290(1) مطابق با استاندارد براي پرتونگاري طبق III يا II سطح NDT فقط كاركنان بايد تصاوير پرتونگاري را تفسير نمايند. SNT-TC-1A
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Y.Norouzian | Signature |  |  |  | Clarified By: | Signature
| Date: 06-06-23 |  |  |  |  | Date: