## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-PR-PF-0001 |  |  |  |  | Vendor Tr. N0: |  |  | Transmital Date:
Document Title: PROCESS FLOW DIAGRAMS |  |  |  |  | Client Tr. No: BK-HD-PEDCO-SVTR-HY-0028 |  |  | Transmital Date: 2023/11/12
[5 empty] | CRS No:PECO- CRS-BK-GCS-HY-120-PR-PF-0001-V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مسیر Spill Back مطابق نقشه های P&ID ایستگاه تصحیح گردد. |  | BK-SUR-ENG-MEC-02-08545 | 2023-10-04 | هوایار: تغییرات لازم درج خواهد شد.
2 | مطابق توضیحات سازنده در جلسه 1402/07/09 جریان شماره 8 در Summer case دارای مقدار کمی آب می باشد که این مساله در Vapor fraction این جریان دیده نمی شود. |  | BK-SUR-ENG-MEC-02-08545 | 2023-10-04 | هوایار: بررسی خواهد شد.
3 | بر اساس اطلاعات خروجی سازنده کمپرسور، مدرک PFD ایستگاه و همچنین درصورت نیاز اطلاعات ورودی سازنده های بخش های دیگر همچون کولرهای هوایی بازنگری گردد. |  | BK-SUR-ENG-MEC-02-08545 | 2023-10-04 | هوایار: داده های فرایندی کمپرسور در مدارک مربوطه ارائه شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 04/10/2023 |  |  |  |  | Date: