## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-HY-120-IN-DG-0002
Document Title:OVERAL CONTROL/SAFETY SYSTEM CONFIGURATION DIAGRAM |  |  |  |  | PEDCO Tr. No.:BK-HD-PEDCO--SVTR-HY-0033 |  |  | Transmital Date:2023/12/06
[5 empty] | CRS No:NISOC-CRS-BK-GCS-HY-120-IN-DG-0002_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02/2294/359347 | 1402/09/06 | شبکه بین UCP و FCP نشان داده شده است. جهت پیکر بندی داخلی تابلو Note اضافه می شود.
2 |  |  | 02/2294/359347 | 1402/09/06 | نحوه ارتباط OWS با PLC در صفحه دوم موجود است.
3 |  |  | 02/2294/359347 | 1402/09/06 | به هیرگان تبدیل می شود.
4 |  |  | 02/2294/359347 | 1402/09/06 | مورد تایید است.
Process comments :
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 17 Jul 2023 |  |  |  |  | Date: