## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-HY-120-IN-DS-0004_V01 |  |  |  |  | Vendor Tr. N0: BK-HD-PEDCO-SVTR-HY-0041 |  |  | Transmital Date: 6 Nov 2023
Document Title: DATASHEET FOR SAFETY VALVES |  |  |  |  | Client Tr. No: |  |  | Transmital Date:
[5 empty] | CRS No:PECO- CRS-BK-GCS-HY-120-IN-DS-0004-V01 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بر اساس مذاکرات انجام گرفته در خصوص صحت بررسی مدارک سازندگان و همچنین مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) و سازنده مي باشد. |  | BK-SUR-ENG-MEC-02-08807 | 2023-11-21
2 | سایز خط در line no مربوط به PSV-2192 و PSV-2193 پس از نهایی سازی موقعیت reducer چک و اصلاح گردد. همچنین در line no مذکور، کد PT به IS تصحیح گردد. |  | BK-SUR-ENG-MEC-02-08807 | 2023-11-21
3 | با توجه به اینکه PSVهای خروجی کمپرسور هر دو مرحله ( PSV-2192 تا PSV-2195 ) خارج از Package قرار دارد پیشنهاد می شود Tag no آنها مطابق PID شرکت هیرگان مدنظر قرار گیرد. |  | BK-SUR-ENG-MEC-02-08807 | 2023-11-21
4 | شماره صفحه sheet No. در قسمت P&ID ها ذكر گردد |  | BK-SUR-ENG-MEC-02-08807 | 2023-11-21
5 | سايزهاي ورودي و خروجي در P&ID مشخص گردد. |  | BK-SUR-ENG-MEC-02-08807 | 2023-11-21
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri P.Maleki S.Akbari | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 21/11/2023 |  |  |  |  | Date: