## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-HY-120-IN-DS-0001_V01
Document Title: INSTRUMENT DATASHEETS / CERTIFICATES |  |  |  |  | PEDCO Tr. No.:BK-HD-PEDCO-SVTR-HY-0040 |  |  | Transmital Date:2023/12/12
[5 empty] | CRS No:NISOC-CRS-BK-GCS-HY-120-IN-DS-0001_V01 |  |  | CRS Status: | CM
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 02/2294/359370 | 1402/09/06 | احتراما با آخرین P&ID چک شود ( R04 )
2 |  |  | 02/2294/359370 | 1402/09/06 | روی اسکید نصب نمی گردد و روی خطوط بین اسکید است.
3 |  |  | 02/2294/359370 | 1402/09/06 | اصلاح شد
4 |  |  | 02/2294/359370 | 1402/09/06 | مشخص شد.
5 |  |  | 02/2294/359370 | 1402/09/06 | موجود است.
6 |  |  | 02/2294/359370 | 1402/09/06 | اصلاح شد ( برای فشار- دما- فلو )
7 |  |  | 02/2294/359370 | 1402/09/06 | اصلاح شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: s.akbari | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
| Date: 10/7/2023 |  |  |  |  | Date: